## График (hidden)
График приобретения оборудования участка сгущения и фильтрации Pb-Zn концентрата ОФ Маднеули.
| № | ЭТАПЫ ПРОЕКТА | Стоимость | Стоимость, USD | 2022-11-02 |  |  |  | 2022-12-02 |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-04 |  |  |  | 2023-04-04 |  |  |  | 2023-05-05 |  |  |  | 2023-06-05 |  |  |  | 2023-07-06 |  |  |  | 2023-08-06 |  |  |  | 2023-09-06 |  |  |  | 2023-10-07 |  |  |  | 2023-11-07 |  |  |  | 2023-12-08 |  |  |  | 2024-01-08 |  |  |  | 2024-02-08 |  |  |  | 2024-03-10 |  |  |  | 2024-04-10 |  |  |  | 2024-05-11
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
СГУЩЕНИЕ | 1 | Zn TAILINGS THICKENER FEED TANK | 20000 | bar: 2023-05-05 1 to 2023-08-06 4
| 2 | Zn TAILINGS THICKENER UNDERFLOW PUMP | 20000 | bar: 2023-05-05 1 to 2024-05-11 24
| 3 | Zn TAILINGS THICKENER UNDERFLOW PUMP | 20000 | bar: 2023-05-05 1 to 2024-05-11 24
| 4 | Zn TAILINGS FILTER FEED SURGE TANK | 20000 | bar: 2023-05-05 1 to 2023-08-06 4
| 5 | Zn TAILINGS PRESSURE FILTER FEED PUMP | 25000 | bar: 2023-05-05 1 to 2024-05-11 24
| 6 | Zn TAILINGS PRESSURE FILTER FEED PUMP | 25000 | bar: 2023-05-05 1 to 2024-05-11 24
|  | ИТОГО ПО СГУЩЕНИЮ: | 130000
ФИЛЬТРАЦИЯ | 8 | Zn TAILINGS FILTRATE PUMP BOX | 20000 | bar: 2023-05-05 1 to 2023-08-06 4
| 9 | Zn TAILINGS FILTRATE RELEASE PUMP | 10000 | bar: 2023-05-05 1 to 2024-05-11 24
| 10 | Zn TAILINGS FILTRATE RELEASE PUMP | 10000 | bar: 2023-05-05 1 to 2024-05-11 24
|  | ИТОГО ПО ФИЛЬТРАЦИИ | 40000
ВОЗДУХОСНАБЖЕНИЕ | 15 | Atlas Copco GA315 | 140000 | bar: 2023-05-05 1 to 2023-12-08 4
| 16 | Air receiver 10m3 | 10000 | bar: 2023-05-05 1 to 2023-12-08 4
| 17 | Air receiver 40m3 | 40000 | bar: 2023-05-05 1 to 2023-12-08 4
| 18 | Air receiver 4m3 | 4000 | bar: 2023-05-05 1 to 2023-12-08 4
| 20 | LT20-20UV TM 250 400/3/50 CE | 9000 | bar: 2023-05-05 1 to 2023-12-08 4
| 22 | Atlas Copco OSC2500 Organo Clay oil/ water condensate separator | 6000 | bar: 2023-05-05 1 to 2023-12-08 4
|  | ИТОГО ПО ВОЗДУХОСНАБЖЕНИЮ | 209000
АСУТП и КИП, ЭНЕРГЕТИКА | 23 | МСС | 250000 | bar: 2023-05-05 1 to 2023-08-06 4
| 24 | Датчики КИП | 70000 | bar: 2023-05-05 1 to 2023-10-07 4
| 25 | Система DCS (включая шкафы ПЛК, Сервер, АРМы) | 50000 | bar: 2023-05-05 1 to 2024-01-08 8
| 26 | Кабели с лотками | 30000 | bar: 2023-05-05 1 to 2023-06-05 4
| 27 | Монтаж КИПиА, кабелей КИПиА | 20000 | bar: 2023-05-05 1 to 2024-01-08 8
| 28 | ПНР АСУ ТП | 100000 | bar: 2023-05-05 1 to 2024-01-08 8; 2024-03-10 13 to 2024-05-11 24
|  | ИТОГО ПО АСУТП и КИП, ЭНЕРГЕТИКА | 520000 | bar: 2023-05-05 1 to 2024-01-08 8; 2024-03-10 13 to 2024-05-11 24
|  | ИТОГО ПО ОБОРУД | 899000
Параметр
Плечо откатки
Грузоподъемность самосвала
Средняя скорость движения
Время 1 рейса
Время работы
Производительность 1 автосамосвала в смену
Объем отсыпки 1 этап
Период отсыпки 1 этапа
Необходимые объемы отсыпки
Необходимо автосамосвалов
Комментарии:
| 1 | 24.01.23-подписан договор между проектной организацией (МИГРУП) и RMG
| 2 | 27.01.23-получен инвойс на оплату аванса, инвойс согласован ИД, оплата ожидается до 3.02.
| 3 | Идет подготовка пакета документов для забора груза из Ставрополя и оформление временного ввоза в Грузию, ожидаем отправку груза до 10.02.
| 4 | В феврале назначена встреча с МИГРУП в Казрети по проекту 38 яруса и дальнейшего поддержания в работоспособном состоянии Маднеульского ХХ
| 5 | Программа изыскательных работ на согласована
6
| 7 | Проводиться работа по врененному ввозу материалов для бурения в Грузию.
| 8 | Начата работа по подготовки документов (ПЗ) для министерства экологии (описание, расчеты).
|  | СМР | 397176 | bar: 2023-05-05 1 to 2023-10-07 4
|  | ИТОГО ПО ПРОЕКТУ | 1296176

## Существующее ФСО (hidden)
Существующее ФСО
№ | Наименование работ | Ед Изм | Объём | Ед Ст-сть, $ | Стоимость, $ | Нед 1 | Нед 2 | Нед 3 | Нед 4 | Нед 5 | Нед 6 | Нед 7 | Нед 8 | Нед 9 | Нед 10 | Нед 11 | Нед 12 | Нед 13 | Нед 14 | Нед 15 | Нед 16 | Нед 17 | Нед 18 | Нед 19 | Нед 20 | Нед 21 | Нед 22 | Нед 23
1 | Демонтажные работы для устроисто фундамента фильтра
1.1 | Демонтаж существующих простенок | м³ | 250 |  | 0 | bar: Нед 1 to Нед 2
1.2 | Демонтаж существуюшегося полового бетонного перекрития в осях А и Б | м² | 700 |  | 0 | bar: Нед 1 to Нед 2
1.3 | Усиление оставшихся консольных частей балок в осях А и Б | шт | 8 | 2500 | 20000 | bar: Нед 2 to Нед 4
1.4 | Вырезка мет балок в местах возведения ж/б фундаментов для фильтров в осях А и Б | шт | 4 |  | 0 | bar: Нед 13 to Нед 14
| Промежуточная сумма |  |  |  | 20000
2 | Ж/Б работы для фундамента фильтра
2.1 | Земляные работы и устроиство щебеночной подготовки под фундамент фильтра | м³ | 150 | 20 | 3000 | bar: Нед 3 to Нед 4
2.2 | Устроиство фундаментной плиты для фильтра | м³ | 114 | 310 | 35340 | bar: Нед 5 to Нед 10
2.3 | Устроиство ж/б колонн фундамента фильтра | м³ | 55 | 310 | 17050 | bar: Нед 11; Нед 15
2.4 | Устроиство ж/б промежуточной плиты для конвейера под филтром | м³ | 45 | 310 | 13950 | bar: Нед 12
2.5 | Устроиство ж/б ригелей фундамента фильтра | м³ | 41 | 310 | 12710 | bar: Нед 16 to Нед 18
2.6 | Устроиство полов с уклонами и питами на первом етаже | м³ | 240 | 210 | 50400 | bar: Нед 13 to Нед 16
| Промежуточная сумма |  |  |  | 132450
3 | Металичесский каркас для полов, обсл площадок и усиление конструктива
3.1 | Устроиство мет каркаса для просечек | Тонн | 6 | 2500 | 15000 | bar: Нед 19 to Нед 21
3.2 | Покраска МК | литр | 400 | 15 | 6000 | bar: Нед 5 to Нед 8; Нед 20 to Нед 22
3.3 | Укладка посечек | м² | 700 | 90 | 63000 | bar: Нед 21 to Нед 23
| Промежуточная сумма |  |  |  | 84000
| Сумма по устроиству фундамента фильтра |  |  |  | 236450
4 | Подготовительные работы для устроиства фундамента сгустителья
4.1 | Демонтаж существующих лестниц |  |  |  | 0 | bar: Нед 1
4.2 | Реабилитация системы существующей канализации |  |  |  | 0 | bar: Нед 2 to Нед 8
4.3 | Земляные работы и устроиство щебеночной подготовки под фундамент сгустителья | м³ | 293 | 20 | 5860 | bar: Нед 9 to Нед 11
4.4 | Устроиство бетонной подготовки под фундамент сгустителья | м³ | 32 | 200 | 6400 | bar: Нед 12
| Промежуточная сумма |  |  |  | 12260
5 | Ж/Б работы для фундамента сгустителья
5.1 | Устроиство фундаментной плиты для сгустителья | м³ | 192 | 310 | 59520 | bar: Нед 13 to Нед 18
5.2 | Устроиство ж/б колонн фундамента фильтра | м³ | 28 | 310 | 8680 | bar: Нед 19 to Нед 20
5.5 | Устроиство стены, уклонов и пита под сгуститель | м³ | 67 | 210 | 14070 | bar: Нед 21 to Нед 23
| Промежуточная сумма |  |  |  | 82270
| Сумма по устроиству фундамента сгустителя |  |  |  | 94530
| Общая сумма |  |  |  | 330980
| Непредвиденные расходы |  | % | 0.2 | 66196
397176

## Zn хвосты по проекту (hidden)
|  |  |  | Customer | JSC RMG Auramine LLC |  |  |  | By | Date
|  |  |  | Project Name | Beqtaqari Detailed Engineering |  |  | Prepared | MHA | 23/05/2022
|  |  |  | Project Number | P1384 |  |  | Checked | LRU | 2022-10-28
|  |  |  | Document Name | Equipment List |  |  | Released | ESA | 2022-09-26
|  |  |  | Document Number | P1384-000-PR-001-8
|  |  |  | Revision | 8
NO ZONE | DESCR. | #ITEM | EQUIPMENT TAG | Equipment Description | Equipment Name | Supply by | Equipment sizing done by | Model | Critical Load | VFD | POWER, kW Installed | Stby | MCC | PLC | INFORMATION SOURCE | Comments
100 | SC | 001 | 100-SC-001 | Screen | Static grizzly screen |  | Chemitec/Proton | Opening size: 560 mm |  |  | 0
100 | HP | 001 | 100-HP-001 | Hopper | Hopper |  | Chemitec/Proton | Volume 50 m3 |  |  | 0
100 | CH | 001 | 100-CH-001 | Chute | Grizzly Feeder Feed Chute |  | Proton |  |  |  | 0
100 | GF | 001 | 100-FE-001 | Grizzly Feeder | Grizzly Feeder | Metso Outotec | Chemitec/Metso Outotec | TKF11-42-2V |  | X | 12 |  | X | X | P202110.01-E01_MCC_PROJECT-Rev03 | Power has updated on 8.9.2022. Power is taken from Vendor-MCC Project document. Power includes auxilary equipment for Crushing Unit (Grizzly Feeder+ Jaw crusher), which is 2 kW
100 | CH | 002 | 100-CH-002 | Chute | Grizzly Feeder Fine Chute |  | Proton |  |  |  | 0
100 | CH | 003 | 100-CH-003 | Chute | Grizzly Feeder Discharge Chute |  | Proton |  |  |  | 0
100 | CR | 001 | 100-CR-001 | Crusher | Jaw Crusher | Metso Outotec | Chemitec/Metso Outotec | C 106 Series |  |  | 110 |  | X | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 MCC & 1 PLC for Crushing Unit (Greezly Feeder & Crusher) is included in Vendor Scope.
100 | CH | 004 | 100-CH-004 | Chute | Jaw Crusher Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 001 | 100-CV-001 | Belt Conveyor | Conveyor 1 | Birikim | Birikim | 5° slope |  |  | 4 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 005 | 100-CH-005 | Chute | Conveyor 1 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CV | 002 | 100-CV-002 | Belt Conveyor | Conveyor 2 | Birikim | Birikim | 10° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
100 | WT | 001 | 100-WT-001 | Weightometer | Weightometer | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 006 | 100-CH-006 | Chute | Conveyor 2 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | DM | 001 | 100-ST-001 | Storage | Crushed Ore Storage |  | Proton |  |  |  | 0
100 | CH | 007 | 100-CH-007 | Chute | Apron Feeder Feed 1 Chute |  | Proton |  |  |  | 0
100 | CH | 008 | 100-CH-008 | Chute | Apron Feeder Feed 2 Chute |  | Proton |  |  |  | 0
100 | CH | 009 | 100-CH-009 | Chute | Apron Feeder Feed 3 Chute |  | Proton |  |  |  | 0
100 | AF | 001 | 100-AF-001 | Apron feeder | Apron Feeder 1 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | AF | 002 | 100-AF-002 | Apron feeder | Apron Feeder 2 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 set of PLC for 3 Apron Feeders is included in Vendor Scope.
100 | AF | 003 | 100-AF-003 | Apron feeder | Apron Feeder 3 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | CH | 010 | 100-CH-010 | Chute | Apron Feeder 1 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 011 | 100-CH-011 | Chute | Apron Feeder 2 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 012 | 100-CH-012 | Chute | Apron Feeder 3 Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 003 | 100-CV-003 | Dribble chute | Conveyor 3 | Birikim | Birikim | 0° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 013 | 100-CH-013 | Chute | Conveyor 3 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CH | 014 | 100-CH-014 | Chute | Apron Feeder 1 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 015 | 100-CH-015 | Chute | Apron Feeder 2 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 016 | 100-CH-016 | Chute | Apron Feeder 3 Fines Chute |  | Proton |  |  |  | 0
100 | DC | 001 | 100-DC-001 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 1.1 |  |  |  | Birikim Offer #211314_R5
100 | FA | 001 | 100-FA-001 | Fan | Dust Collector Fan | Birikim | Birikim | AL-RS1N-B 500 |  |  | 22 |  |  |  | Birikim Offer #211314_R5
100 | RV | 001 | 100-RV-001 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | DC | 002 | 100-DC-002 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 2.2 |  |  |  | Birikim Offer #211314_R5
100 | FA | 002 | 100-FA-002 | Fan | Dust Collector Fan | Birikim | Birikim |  |  |  | 45 |  |  |  | Birikim Offer #211314_R5
100 | RV | 002 | 100-RV-002 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | CN | 001 | 100-CN-001 | Overhead crane | Overhead crane |  | Chemitec/Supplier |  | X | X | 44 |  |  |  | Estimate based on highest power from vendor
100 | MA | 001 | 100-MA-001 | Self cleaning magnet | Self cleaning magnet | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 017 | 100-CH-017 | Chute | Scrap Chute |  | Proton |  |  |  | 0
100 | SP | 001 | 100-SP-001 | SUMP PUMP | Portable Sump Pump Crushing Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
100 | SP | 002 | 100-SP-002 | SUMP PUMP | Portable Sump Pump Stockpile Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 15 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
200 | CV | 1 | 200-CV-001 | Belt conveyor | CONVEYOR | Birikim | Birikim | 13° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 1 | 200-CH-001 | Chute | CONVEYOR DISCHARGE CHUTE | Birikim | Birikim |  |  |  | 0
200 | CV | 2 | 200-CV-002 | Belt conveyor | CONVEYOR | Birikim | Birikim | 10° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | CV | 3 | 200-CV-003 | Belt conveyor | CONVEYOR | Birikim | Birikim | 6° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | MA | 1 | 200-MA-001 | Self cleaning magnet | SELF CLEANING MAGNET | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 1 | 200-WT-001 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 2 | 200-WT-002 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 2 | 200-CH-002 | Chute | SAG MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | SM | 1 | 200-SM-001 | SAG Mill | SAG MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø5.00 m X 2.50 m EGL SAG Mill |  | X | 1044.516 |  |  |  | Power: C.008312-EE-YRK-DWG-00032-01_900113292. MCC & PLC: 3067739 - RMG Beqtaqari- MO Select 5.0 m x 2.5 m EGL SAG Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 Low voltage MCC & 1 PLC for SAG Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 1 | 200-TR-001 | Mill Trommel | SAG MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | JS | 1 | 200-JS-001 | Jacking system | MILL JACKING SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
200 | LN | 1 | 200-LN-001 | Liner Handler | SAG MILL LINER HANDLER | Russell | Chemitec/Supplier |  |  |  | 30 |  |  |  | Russel Offer: Q034634 BEQTAQARI - R3-1000 LINER HANDLER - RAILED 20220302 130353
200 | CH | 3 | 200-CH-003 | Chute | SAG MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | CH | 4 | 200-CH-004 | Chute | SAG MILL REJECT CHUTE |  | Proton |  |  |  | 0
200 | CH | 5 | 200-CH-005 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | CH | 6 | 200-CH-006 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | HP | 1 | 200-BX-001 | Distribution launder | DISTRIBUTION LAUNDER |  | Proton |  |  |  | 0
200 | PB | 1 | 200-PB-001 | Pump Box | PRIMARY PUMP BOX |  | Proton |  |  |  | 0
200 | PP | 1 | 200-PP-001 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | PP | 2 | 200-PP-002 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | CY | 1 | 200-CY-001 | Hydrocyclone | BALL MILL CYCLONE 1 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CY | 2 | 200-CY-002 | Hydrocyclone | BALL MILL CYCLONE 2 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CH | 7 | 200-CH-007 | Chute | BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | BM | 1 | 200-BM-001 | Ball Mill | BALL MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø3.40 m X 5.95 m EGL Ball Mill |  |  | 996.716 |  | X | X | Power: C.008312-EE-YRK-DWG-00040-02_900113293, MCC &PLC: 3067739 - RMG Beqtaqari - MO Select 3.4 m x 5.95 m EGL Ball Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 LW MCC & 1 PLC for Ball Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 2 | 200-TR-002 | Mill Trommel | BALL MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | CH | 8 | 200-CH-008 | Chute | BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | PT | 1 | 200-PT-001 | Scats Hopper | SCATS HOPPER |  | Proton |  |  |  | 0
200 | BN | 1 | 200-BN-001 | Ball pits | BALL PIT | RMG | Chemitec |  |  |  | 0
200 | MA | 1 | 200-MA-001 | Ball magnet | BALL MAGNET |  | Supplier |  |  |  | TBD |  |  |  | RMG to provide power
200 | BB | 1 | 200-BB-001 | Ball bucket | BALL BUCKET |  | Supplier |  |  |  | 0
200 | CH | 9 | 200-CH-009 | Chute | BALL CHARGER CHUTE |  | Supplier |  |  |  | 0
200 | CN | 1 | 200-CN-001 | Overhead crane | GRINDING AREA OVERHEAD CRANE |  | Chemitec |  | X | X | 60.4 |  |  |  |  | Preliminary power estimated by highest consumer offered
200 | BX | 4 | 200-BX-004 | Pebbles Box | PEBBLES BOX |  | Proton |  |  |  | 0 |  |  |  |  | Added 16.8.2022
200 | SP | 1 | 200-SP-001 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 2 | 200-SP-002 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 3 | 200-SP-003 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
300 | SA | 1 | 300-SA-001/2 | Process Sampler | FLOTATION FEED (LSA SAMPLER (PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 1 | 300-SV-001/2 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-001/2 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 1 | 300-SA-001/1 | Metallurgical Sampler | FLOTATION FEED (MSA SAMPLER (EA)) | Metso Outotec | Chemitec |  |  |  | 15
300 | TK | 1 | 300-TK-001 | Tank | BULK ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
300 | AG | 1 | 300-AG-001 | AGITATOR | AGITATOR FOR BULK CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 15 |  |  |  | Offer SPX : 30966,30977
300 | FC | 1 | 300-FC-001 | Flotation Cell | BULK ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 2 | 300-FC-002 | Flotation Cell | BULK ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 3 | 300-FC-003 | Flotation Cell | BULK ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 4 | 300-FC-004 | Flotation Cell | BULK ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 5 | 300-FC-005 | Flotation Cell | BULK ROUGHER CELL 5 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 6 | 300-FC-006 | Flotation Cell | BULK SCAVENGER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 7 | 300-FC-007 | Flotation Cell | BULK SCAVENGER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | CH | 3 | 300-CH-003 | Launder | CELLS 001-005 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | CH | 4 | 300-CH-004 | Launder | CELLS 006-007 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 4 | 300-PB-004 | Pump Box | BULK ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 9 | 300-PP-009 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 10 | 300-PP-010 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PB | 3 | 300-PB-003 | Pump Box | BULK SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 7 | 300-PP-007 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 8 | 300-PP-008 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 3 | 300-SA-003 | Process Sampler | BULK SCAVENGER CONCENTARET (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
300 | SV | 3 | 300-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | PB | 1 | 300-PB-001 | Pump Box | SCAVENGER TAILING PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 3 | 300-PP-003 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 4 | 300-PP-004 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 2 | 300-SA-002 | Metallurgical Sampler | BULK SCAVENGER TAILINGS (MSA SAMPLER (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
300 | CY | 1 | 300-CY-001 | Hydrocyclone | REGRIND CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | CY | 2 | 300-CY-002 | Hydrocyclone | REGRIND CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | BX | 1 | 300-BX-001 | Distribution Box | DISTRIBUTION BOX 1 |  | Proton |  |  |  | 0
300 | CH | 1 | 300-CH-001 | Chute | REGRIND BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
300 | BM | 1 | 300-BM-001 | Ball Mill | REGRIND BALL MILL | CEMTEC | Chemitec/CEMTEC | Wet Ball Mill Ø2.40 m X 3.75 m |  |  | 254.61 |  |  | X | 208206-740-100-MBM-ELA001-00, Appendix 1_A113245-05_commercial_offer_ball_mill | Power includes auxiliaries
300 | TR | 1 | 300-TR-001 | Mill Trommel | REGRIND BALL MILL TROMMEL | CEMTEC | CEMTEC |  |  |  | 0
300 | CH | 1 | 300-CH-002 | Chute | REGRIND BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 2 | 300-PB-002 | Pump Box | REGRIND CYCLONE FEED PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 5 | 300-PP-005 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 6 | 300-PP-006 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 5 | 300-SA-005 | Process Sampler | Pb ROUGHER FEED-GOING TO Zn COND.(LSA SAMPLER (EA&PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 5 | 300-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 4 | 300-SA-004 | Process Sampler | Pb ROUGHER FEED-LSA SAMPLER (EA&PSD) |  | Chemitec |  |  |  | 0
300 | SV | 4 | 300-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | CN | 1 | 300-CN-001 | Overhead Crane | BULK FLOTATION AND REGRINDING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
300 | SP | 1 | 300-SP-001 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 2 | 300-SP-002 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 3 | 300-SP-003 | SUMP PUMP | SUMP PUMP REGRINDING BALL MILL | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | ES | 1 | 300-ES-001 | Emergency Station | EMERGENCY SHOWER & EYE WASH STATION |  | Proton |  |  |  | 0
305 | TK | 1 | 305-TK-001 | TANK | TAILINGS THICKENER FEED TANK |  | Chemitec/Proton | 4 m3 |  |  | 0
305 | RA | 1 | 305-RA-001 | RAKE MECHANISM | TAILINGS THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 4 |  |  |  | 3274949 Technical Description rev.06
305 | TH | 1 | 305-TH-001 | THICKENER | TAILINGS THICKENER | Metso Outotec | Chemitec | HRT - 16 m | X |  | 1.5 |  |  |  | OU500759567_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
305 | PP | 1 | 305-PP-001 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 2 | 305-PP-002 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | TK | 2 | 305-TK-002 | TANK | TAILINGS FILTER FEED SURGE TANK |  | Chemitec/Proton | 250 m3 |  |  | 0
305 | AG | 2 | 305-AG-002 | AGITATOR | AGITATOR FOR TAILINGS FILTER FEED SURGE TANK |  | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
305 | PP | 5 | 305-PP-005 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 6 | 305-PP-006 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | FL | 1 | 305-FL-001 | FILTER PRESS | TAILINGS FILTER | Diemme | Chemitec/Diemme | ME 2000 F15 |  |  | 49.62 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Bulk Tailings Filter Press is included in Vendor Scope.
305 | PB | 2 | 305-PB-002 | PUMP BOX | TAILINGS THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 8 | 305-PP-008 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | CH | 1 | 305-CH-001 | CHUTE | TAILINGS PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
305 | CV | 1 | 305-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-1000 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 2 | 305-CV-002 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | XE400 2+2 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 3 | 305-CV-003 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125, 2+2 |  |  | 11 |  |  |  | Birikim Offer # 211600 R2
305 | BN | 1 | 305-BN-001 | TAILINGS SILO | TAILINGS SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
305 | CN | 1 | 305-CN-001 | OVERHEAD CRANE | TAILINGS DEWATERING OVERHAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
305 | SP | 1 | 305-SP-001 | SUMP PUMP | SUMP PUMP FOR TAILINGS THICKENER AREA | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 2 | 305-SP-002 | SUMP PUMP | SUMP PUMP FOR TAILINGS FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 3 | 305-SP-003 | SUMP PUMP | FILTER WASHING AND RINSING WASHING SUMP PUMP | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | TK | 4 | 305-TK-004 | TANK | FILTER WASHING WATER TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 200 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | P&ID shows 137 kW. (MH: 137 might me working power)
305 | PP | 8 | 305-PP-008 | PUMP | HIGH PRESSURE WASHING PUMP | Diemme | Diemme | Piston type pump |  | X | 37 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
310 | TK | 1 | 310-TK-001 | Tank | Pb ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-001 | AGITATOR | AGITATOR FOR Pb CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | FC | 1 | 310-FC-001 | Flotation Cell | Pb ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 2 | 310-FC-002 | Flotation Cell | Pb ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 3 | 310-FC-003 | Flotation Cell | Pb ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 4 | 310-FC-004 | Flotation Cell | Pb ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 5 | 310-FC-005 | Flotation Cell | Pb SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | PB | 1 | 310-PB-001 | Pump Box | DEWATERING CYCLONES FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 1 | 310-PP-001 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 2 | 310-PP-002 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 8 | 310-PB-008 | Pump Box | Pb SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 17 | 310-PP-017 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 18 | 310-PP-018 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | CY | 1 | 310-CY-001 | Hydrocyclone | DEWATERING CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | CY | 2 | 310-CY-002 | Hydrocyclone | DEWATERING CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | HP | 1 | 310-HP-001 | Grinding Media Addition System | MEDIA ADDITION SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
310 | BN | 1 | 310-BN-001 | Bin | MEDIA HANDLING BIN | Metso Outotec | Metso Outotec |  |  |  | 0
310 | HP | 1 | 310-HP-001 | Hopper | MEDIA HOPPER | Metso Outotec | Metso Outotec |  |  |  | 0
310 | SD | 1 | 310-SD-001 | Mill | FINE GRIND MILL | Metso Outotec | Metso Outotec | SMD-E-90 |  |  | 92.41 |  |  |  | C.008574-EE-YRK-DWG-00030 | Including auxiliary equipment
310 | PB | 2 | 310-PB-002 | Pump Box | Pb 1st CLEANER FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 3 | 310-PP-003 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 4 | 310-PP-004 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 2 | 310-SA-002 | Process Sampler | Pb ROUGHER CONCENTRATE (ASA SAMPLER (EA & PSD)) |  | Chemitec |  |  |  | 0
310 | SV | 6 | 310-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SV | 2 | 310-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | TK | 2 | 310-TK-002 | Tank | Pb 1st CLEANER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-002 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 1 | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | TK | 3 | 310-TK-003 | Tank | Pb 1st CLEANER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 3 | 310-AG-003 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 2 | SPX Flow | Supplier |  | X |  | 3 |  |  |  | Offer SPX : 30966,30977
310 | FC | 6 | 310-FC-006 | Flotation Cell | Pb 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 7 | 310-FC-007 | Flotation Cell | Pb 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 8 | 310-FC-008 | Flotation Cell | Pb 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | SA | 4 | 310-SA-004 | Process Sampler | Pb 1st CLEANER TAILING (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 4 | 310-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 3 | 310-PB-003 | Pump Box | Pb 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 5 | 310-PP-005 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 6 | 310-PP-006 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 9 | 310-FC-009 | Flotation Cell | Pb 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 10 | 310-FC-010 | Flotation Cell | Pb 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | PB | 4 | 310-PB-004 | Pump Box | Pb 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 7 | 310-PP-007 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 8 | 310-PP-008 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 9 | 310-PB-009 | Pump Box | Pb 2nd CLEANER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 19 | 310-PP-019 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 20 | 310-PP-020 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 5 | 310-SA-005 | Process Sampler | Pb 2nd CLEANER CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 5 | 310-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | FC | 11 | 310-FC-011 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 12 | 310-FC-012 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 13 | 310-FC-013 | Flotation Cell | Pb 3rd CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | SA | 6 | 310-SA-006 | Process Sampler | Pb 3rd CLEANER TAILINGS (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | PB | 5 | 310-PB-005 | Pump Box | Pb 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 9 | 310-PP-009 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 10 | 310-PP-010 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 14 | 310-FC-014 | Flotation Cell | Pb 4th CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 15 | 310-FC-015 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 16 | 310-FC-016 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | PB | 6 | 310-PB-006 | Pump Box | Pb 4th CLEANER CONC. PUMP BOX |  | Chemitec |  |  | X | 0
310 | PP | 11 | 310-PP-011 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 12 | 310-PP-012 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 1 | 310-SA-001 | Metallurgical Sampler | Pb FINAL CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 1 | 310-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 10 | 310-PB-010 | Pump Box | Pb TAILINGS DISCHARGE PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 13 | 310-PP-013 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 14 | 310-PP-014 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 3 | 310-SA-003 | Process Sampler | Pb TAILINGS (PSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 3 | 310-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SP | 1 | 310-SP-001 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 2 | 310-SP-002 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 3 | 310-SP-003 | SUMP PUMP | SUMP PUMP FINE GRINDING MILL | Metso Outotec | Metso Outotec / Chemitec | VS25 L80 O5D85 HC | X | X | 2.2 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | CH | 1 | 310-CH-001 | Launder | Pb Rougher Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 2 | 310-CH-002 | Launder | Pb Rougher Scav Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 3 | 310-CH-003 | Launder | Pb 1st cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 4 | 310-CH-004 | Launder | Pb 2nd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 5 | 310-CH-005 | Launder | Pb 3rd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 6 | 310-CH-006 | Launder | Pb 4th cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | TK | 1 | 320-TK-001 | Tank | Zn ROUGHER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 1 | 320-AG-001 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 1 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | TK | 2 | 320-TK-002 | Tank | Zn ROUGHER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 2 | 320-AG-002 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 2 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | FC | 1 | 320-FC-001 | Flotation Cell | Zn ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 2 | 320-FC-002 | Flotation Cell | Zn ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 3 | 320-FC-003 | Flotation Cell | Zn ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 4 | 320-FC-004 | Flotation Cell | Zn SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | PB | 1 | 320-PB-001 | Pump Box | Zn ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 1 | 320-PP-001 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 2 | 320-PP-002 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 1 | 320-SA-001 | Process Sampler | Zn ROUGHER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 1 | 320-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SA | 7 | 320-SA-007 | Process Sampler | Zn ROUGHER SCAVENGER TAILINGS (LSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 7 | 320-SV-007 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-007 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 7 | 320-PB-007 | Pump Box | Zn SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 13 | 320-PP-013 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 14 | 320-PP-014 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 2 | 320-PB-002 | Pump Box | Zn ROUGHER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 3 | 320-PP-003 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 4 | 320-PP-004 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 3 | 320-SA-003 | Metallurgical Sampler | Zn TAILINGS (MSA Sampler (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
320 | FC | 5 | 320-FC-005 | Flotation Cell | Zn 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 6 | 320-FC-006 | Flotation Cell | Zn 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 7 | 320-FC-007 | Flotation Cell | Zn 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 8 | 320-FC-008 | Flotation Cell | Zn 1st CLEANER SCAVENGER CELL | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 2 | 320-SA-002 | Process Sampler | Zn 1st CLEANER-SCAVENGER TAILINGS (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 2 | 320-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 6 | 320-PB-006 | Pump Box | Zn 1st CLEANER SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 11 | 320-PP-011 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 12 | 320-PP-012 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 3 | 320-PB-003 | Pump Box | Zn 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 5 | 320-PP-005 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 6 | 320-PP-006 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 5 | 320-SA-005 | Process Sampler | Zn 1st CLEANER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 5 | 320-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | FC | 9 | 320-FC-009 | Flotation Cell | Zn 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 10 | 320-FC-010 | Flotation Cell | Zn 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 6 | 320-SA-006 | Process Sampler | Zn 2nd CLANER TAILINGS (ADAPTED RD SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 6 | 320-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 4 | 320-PB-004 | Pump Box | Zn 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 7 | 320-PP-007 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5. |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 8 | 320-PP-008 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | FC | 11 | 320-FC-011 | Flotation Cell | Zn 3rd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 12 | 320-FC-012 | Flotation Cell | Zn 3rd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | PB | 5 | 320-PB-005 | Pump Box | Zn 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 9 | 320-PP-009 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 10 | 320-PP-010 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 15 | 320-PP-015 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 16 | 320-PP-016 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 4 | 320-SA-004 | Metallurgical Sampler | Zn FINAL CONCENTRATE- RD SAMPLER (EA) |  | Chemitec |  |  |  | 0
320 | SV | 4 | 320-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SP | 1 | 320-SP-001 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | SP | 2 | 320-SP-002 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | CH | 1 | 320-CH-001 | Launder | Zn Rougher Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 2 | 320-CH-002 | Launder | Zn Rougher Scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 3 | 320-CH-003 | Launder | Zn 1st cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 4 | 320-CH-004 | Launder | Zn 1st cl scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 5 | 320-CH-005 | Launder | Zn 2nd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 6 | 320-CH-006 | Launder | Zn 3rd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
325 | TK | 1 | 325-TK-001 | TANK | Zn TAILINGS THICKENER FEED TANK |  | Chemitec/Proton | 12 m3 |  |  | 0
325 | RA | 1 | 325-RA-001 | RAKE MECHANISM | Zn TAILINGS THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 5.5 |  |  |  | 3274949 Technical Description rev.06
325 | TH | 1 | 325-TH-001 | THICKENER | Zn TAILINGS THICKENER | Metso Outotec | Chemitec | HCT - 12 m | X |  | 1.5 |  |  |  | OU500759580_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
325 | PP | 1 | 325-PP-001 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 2 | 325-PP-002 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | TK | 2 | 325-TK-002 | TANK | Zn TAILINGS FILTER FEED SURGE TANK |  | Chemitec/Proton | 250 m3 |  |  | 0
325 | AG | 2 | 325-AG-002 | AGITATOR | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
325 | PP | 5 | 325-PP-005 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 6 | 325-PP-006 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | FL | 1 | 325-FL-001 | FILTER PRESS | Zn TAILINGS FILTER | Diemme | Chemitec/Diemme | ME 2000 F13 |  |  | 49.62 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Zn Tailings Filter Press is included in Vendor Scope.
325 | PB | 2 | 325-PB-002 | PUMP BOX | Zn TAILINGS FILTRATE PUMP BOX |  | Chemitec | 30 m3 |  |  | 0
|  |  |  | TANK | PUMP BOX For AGITATOR |  |  | Взять по аналогу от Тех пер Маднеули
AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK |  | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK
325 | PP | 7 | 325-PP-007 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Weir Minerals | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 8 | 325-PP-008 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Weir Minerals | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | CH | 1 | 325-CH-001 | CHUTE | Zn TAILINGS PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
325 | CV | 1 | 325-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-630 |  |  | 9.2 |  |  |  | Birikim Offer # 211600 R2
325 | SP | 1 | 325-SP-001 | SUMP PUMP |  |  | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Will be updated with MOs next rpoposal
325 | SP | 2 | 325-SP-002 | SUMP PUMP |  |  | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
325 | SP | 3 | 325-SP-003 | SUMP PUMP |  |  | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
325 | PP | 9 | 325-PP-009 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 160 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | P&ID shows 132 kW (might be working power)
325 | PP | 10 | 325-PP-010 | PUMP | HIGH PRESSURE WASHING PUMP | Diemme | Diemme | Piston type pump |  | X | 37 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
400 | TK | 1 | 400-TK-001 | TANK | Pb CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 1 | 400-RA-001 | RAKE MECHANISM | Pb CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 1 | 400-TH-001 | THICKENER | Pb CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759542_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 1 | 400-PP-001 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 2 | 400-PP-002 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PB | 1 | 400-PB-001 | PUMP BOX | Pb CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 3 | 400-PP-003 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 4 | 400-PP-004 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 2 | 400-TK-002 | TANK | Pb CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 2 | 400-AG-002 | AGITATOR | AGITATOR FOR Pb CONCENTRATE FEED SURGE TANK |  | SPX Flow | SPX Flow | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 5 | 400-PP-005 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 6 | 400-PP-006 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 1 | 400-FL-001 | FILTER PRESS | Pb CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.1500 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Pb Concentrate Filter Press is included in Vendor Scope.
400 | PB | 1 | 400-PB-003 | PUMP BOX | Pb CONCENTRATE FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 7 | 400-PP-007 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 8 | 400-PP-008 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 1 | 400-CH-001 | CHUTE | Pb CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 1 | 400-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 1 | 400-SA-001 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 2 | 400-CV-002 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 1 | 400-BN-001 | TAILINGS SILO | Pb CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 1 | 400-FE-001 | SCREW EXTRACTOR | Pb CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 1 | 400-BS-001 | BAGGING SYSTEM | Pb CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | SP | 1 | 400-SP-001 | SUMP PUMP | SUMP PUMP FOR Pb CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC |  | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Tag changed. 3.8.2022
400 | PP | 18 | 400-PP-018 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 9.2 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | NOTE CHANGED TAG
400 | TK | 3 | 400-TK-003 | TANK | Zn CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 2 | 400-RA-002 | RAKE MECHANISM | Zn CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 2 | 400-TH-002 | THICKENER | Zn CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759554_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 9 | 400-PP-009 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PP | 10 | 400-PP-010 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PB | 2 | 400-PB-002 | PUMP BOX | Zn CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 11 | 400-PP-011 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 12 | 400-PP-012 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 4 | 400-TK-004 | TANK | Zn CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 4 | 400-AG-004 | AGITATOR | AGITATOR FOR Zn CONCENTRATE FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 13 | 400-PP-013 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 14 | 400-PP-014 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 2 | 400-FL-002 | FILTER PRESS | Zn CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.2700 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Zn Concentrate Filter Press is included in Vendor Scope.
400 | PB | 4 | 400-PB-004 | PUMP BOX | Zn CONCENTRATE THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 15 | 400-PP-015 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 16 | 400-PP-016 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 2 | 400-CH-002 | CHUTE | Zn CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 3 | 400-CV-003 | BELT CONVEYOR | CONVEYOR | Supplier | Supplier | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 2 | 400-SA-002 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 4 | 400-CV-004 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 2 | 400-BN-002 | TAILINGS SILO | Zn CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 2 | 400-FE-002 | SCREW EXTRACTOR | Zn CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 2 | 400-BS-002 | BAGGING SYSTEM | Zn CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | CN | 1 | 400-CN-001 | OVERHEAD CRANE | CONCENTRATE DEWATERING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
400 | PP | 17 | 400-PP-017 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 11 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
400 | SP | 2 | 400-SP-002 | SUMP PUMP | SUMP PUMP FOR Zn CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Added 4.8.2022.
500 | XX | 1 | 500-XX-001 | REAGENT MIXING AND DOSING | MIBC MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.4 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 2 | 500-XX-002 | REAGENT MIXING AND DOSING | AERO 208 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.45 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 3 | 500-XX-003 | REAGENT MIXING AND DOSING | W31 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.18 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 4 | 500-XX-004 | REAGENT MIXING AND DOSING | SODA ASH MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 10.65 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 5 | 500-XX-005 | REAGENT MIXING AND DOSING | Ca(OH)2 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 8.25 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 6 | 500-XX-006 | REAGENT MIXING AND DOSING | DEP347 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.12 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 7 | 500-XX-007 | REAGENT MIXING AND DOSING | ZnSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.23 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 8 | 500-XX-008 | REAGENT MIXING AND DOSING | CuSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 9 | 500-XX-009 | REAGENT MIXING AND DOSING | NaCN MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11.6 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 10 | 500-XX-010 | REAGENT MIXING AND DOSING | SIPX MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 11 | 500-XX-011 | REAGENT MIXING AND DOSING | Magnafloc 1687 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.62 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 12 | 500-XX-012 | REAGENT MIXING AND DOSING | Magnafloc 10 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 3.34 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 13 | 500-XX-013 | REAGENT MIXING AND DOSING | Magnafloc 333 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | SP | 1 | 500-SP-001 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 2 | 500-SP-002 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 3 | 500-SP-003 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 2 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 4 | 500-SP-004 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 3 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 5 | 500-SP-005 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 4 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
600 | CP | 1 | 600-CP-001 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 2 | 600-CP-002 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 |  |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 3 | 600-CP-003 | AIR COMPRESSOR | PLANT AIR COMPRESSOR - STAND BY | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | AR | 1 | 600-AR-001 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AR | 2 | 600-AR-002 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AD | 1 | 600-AD-001 | AIR DRYER | INSTRUMENT AIR DRYER | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0
600 | AD | 2 | 600-AD-002 | AIR DRYER | INSTRUMENT AIR DRYER-STAND BY | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0 | X
600 | AR | 5 | 600-AR-005 | AIR RECEIVER | INSTRUMENT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 10 m3 |  |  | 0
600 | BL | 1 | 600-BL-001 | AIR BLOWER | FLOTATION AIR BLOWER |  | Continental/Chemitec |  |  |  | 160 |  |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | BL | 2 | 600-BL-002 | AIR BLOWER | FLOTATION AIR BLOWER - STAND BY |  | Continental/Chemitec |  |  |  | 160 | X |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | FL | 1 | 600-IF-001 | INLET FILTER | INLET FILTER FOR AIR BLOWER |  | Continental/Chemitec |  |  |  | 0
600 | FL | 2 | 600-IF-002 | INLET FILTER | INLET FILTER FOR AIR BLOWER-STAND BY |  | Continental/Chemitec |  |  |  | 0 | X
600 | CP | 4 | 600-CP-004 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 5 | 600-CP-005 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 6 | 600-CP-006 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | CP | 7 | 600-CP-007 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-5
600 | CP | 8 | 600-CP-008 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-6
600 | CP | 9 | 600-CP-009 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-7
600 | AR | 3 | 600-AR-003 | AIR RECEIVER | FILTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | AR | 4 | 600-AR-004 | AIR RECEIVER | FLTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | TK | 1 | 600-TK-001 | WATER TANK | PROCESS WATER TANK BULK FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 1 | 600-PP-001 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 2 | 600-PP-002 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 2 | 600-TK-002 | WATER TANK | PROCESS WATER TANK Pb FLOTATION |  |  | 30 m3 |  |  | 0
600 | PP | 3 | 600-PP-003 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 4 | 600-PP-004 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 3 | 600-TK-003 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | TK | 4 | 600-TK-004 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 5 | 600-PP-005 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 6 | 600-PP-006 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 5 | 600-TK-005 | WATER TANK | PROCESS WATER TANK BLEEDING TANK |  |  | 20 m3 |  |  | 0
600 | PP | 7 | 600-PP-007 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 8 | 600-PP-008 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 6 | 600-TK-006 | WATER TANK | FRESH WATER TANK |  |  | 300 m3 |  |  | 0
600 | PP | 9 | 600-PP-009 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 10 | 600-PP-010 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 11 | 600-PP-011 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 12 | 600-PP-012 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 7 | 600-TK-007 | WATER TANK | FIRE WATER TANK |  |  | 150 m3 |  |  | 0 |  |  |  | 1. Fire extinguishing system - 380V, 50Hz, 37kW, 97.3 A;
600 | PP | 13 | 600-PP-013 | PUMP | FIRE WATER PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 2. Alarm system - 220V, 500 Watt, 2,3 A; | Information given by RMG on 5.9.2022
600 | PP | 14 | 600-PP-014 | PUMP | FIRE WATER JOCKEY PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 3. Emergency lighting - 220V, 22.4 kW, 100.1 A;
600 | PP | 15 | 600-PP-015 | PUMP | FIRE WATER DIESEL PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 4. Emergency alarm/sirens - 220V, 500 Watt, 2.3A.
600 | SP | 1 | 600-SP-001 | SUMP PUMP | SUMP PUMP Zn-Pb PROCESS WATER TANKS | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 4 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
600 | SP | 2 | 600-SP-002 | SUMP PUMP | SUMP PUMP Zn-Pb TAILINGS, BULK & FRESH WATER TANKS AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
700 | PA | 1 | 700-PA-001 | PARTICLE SIZE ANALYSER | PARTICLE SIZE ANALYSER | Metso Outotec | Chemitec |  |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 4 | 700-MP-004 | MULTIPLEXER | PARTICLE SIZE ANALYSER MULTIPLEXER | Metso Outotec | Chemitec |  |  |  | 0
700 | TK | 1 | 700-TK-001 | TANK | DILUTION WATER TANK | Metso Outotec | Chemitec |  |  |  | 0
700 | EA | 1 | 700-EA-001 | ELEMENTAL ANALYSER | ELEMENTAL ANALYSER | Metso Outotec | Chemitec |  |  |  | 1.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 1 | 700-PP-001 | PUMP | SAMPLE TRANSFER PUMP MXA 1 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 2 | 700-PP-002 | PUMP | SAMPLE TRANSFER PUMP MXA 2 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 4 | 700-PP-004 | PUMP | SAMPLE TRANSFER PUMP PSA - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 1 | 700-MP-001 | MULTIPLEXER | EA MULTIPLEXER 1 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 2 | 700-MP-002 | MULTIPLEXER | EA MULTIPLEXER 2 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 3 | 700-MP-003 | MULTIPLEXER | EA MULTIPLEXER 3 | Metso Outotec | Chemitec |  |  |  | 0
700 | PV | 1 | 700-VP-001 | VERTICAL PUMP | SAMPLE RETURN PUMP 1 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 2 | 700-VP-002 | VERTICAL PUMP | SAMPLE RETURN PUMP 2 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 3 | 700-VP-003 | VERTICAL PUMP | SAMPLE RETURN PUMP 3 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 4 | 700-VP-004 | VERTICAL PUMP | SAMPLE RETURN PUMP 4 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PB | 1 | 700-PB-001 | PUMP BOX | Pb Final Conc. Pump box | [5 empty] | 0
700 | PP | 5 | 700-PP-005 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 6 | 700-PP-006 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 8 | 700-PP-008 | PUMP | DILUTION WATER PUMP | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 3 | 700-PP-003 | PUMP | SAMPLE TRANSFER PUMP MXA 3 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 7 | 700-PP-007 | PUMP | SAMPLE TRANSFER VERTICAL PUMP | Metso Outotec |  | VF50 |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | DP | 1 | 700-DP-001 | DEMULTIPLEXER | DEMULTIPLEXER | Metso Outotec |  |  |  |  | 0 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
999 |  |  |  | Lighting - Main building |  |  |  |  | X |  | 20 |  |  |  | RMG Email from 6.9.2022 | 1. Reserve cells/sections in MCCs – We would prefer to reserve 1 free cell in MCCs for each location (crusher and main building MCCs) with 50kW in order to have spare capacity for connecting additional HVAC, water mist sprayers at ore pad, other equipment.
999 |  |  |  | HVAC - Crusher building |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Stockpile |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Main building |  |  |  |  | X |  | 70
999 |  |  |  | AC for transfromer and MCC room |  |  |  |  | X |  | 50
|  |  |  | PUMP | Zn TAILINGS THICKENER OWERRFLOW PUMP | Weir Minerals |  |  |  |  | 20
|  |  |  | PUMP | Zn TAILINGS THICKENER OWERRFLOW PUMP | Weir Minerals |  |  |  |  | 20
Note on J137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should not be necessary to use, but could be good to have the option.
Note on J219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can send it to the Zn RF or the Bulk RF as long as the valves in the split are energized.
Note on J298: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J368: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Energize pumps, so we can feed soda ash to the NaCN if needed. Also electrical sockets for the portable sump pumps.
Note on J373: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. pH measurement, Fan for gases and fumes and sump pump
Note on J374: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. Fan for gases and fumes and sump pump
Note on J376: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electrical sockets for the portable sump pumps.

## В наличии на складе (hidden)
|  |  |  | Customer | JSC RMG Auramine LLC |  |  |  | By | Date
|  |  |  | Project Name | Beqtaqari Detailed Engineering |  |  | Prepared | MHA | 23/05/2022
|  |  |  | Project Number | P1384 |  |  | Checked | LRU | 2022-10-28
|  |  |  | Document Name | Equipment List |  |  | Released | ESA | 2022-09-26
|  |  |  | Document Number | P1384-000-PR-001-8
|  |  |  | Revision | 8
NO ZONE | DESCR. | #ITEM | EQUIPMENT TAG | Equipment Description | Equipment Name | Supply by | Equipment sizing done by | Model | Critical Load | VFD | POWER, kW Installed | Stby | MCC | PLC | INFORMATION SOURCE | Comments
100 | SC | 001 | 100-SC-001 | Screen | Static grizzly screen |  | Chemitec/Proton | Opening size: 560 mm |  |  | 0
100 | HP | 001 | 100-HP-001 | Hopper | Hopper |  | Chemitec/Proton | Volume 50 m3 |  |  | 0
100 | CH | 001 | 100-CH-001 | Chute | Grizzly Feeder Feed Chute |  | Proton |  |  |  | 0
100 | GF | 001 | 100-FE-001 | Grizzly Feeder | Grizzly Feeder | Metso Outotec | Chemitec/Metso Outotec | TKF11-42-2V |  | X | 12 |  | X | X | P202110.01-E01_MCC_PROJECT-Rev03 | Power has updated on 8.9.2022. Power is taken from Vendor-MCC Project document. Power includes auxilary equipment for Crushing Unit (Grizzly Feeder+ Jaw crusher), which is 2 kW
100 | CH | 002 | 100-CH-002 | Chute | Grizzly Feeder Fine Chute |  | Proton |  |  |  | 0
100 | CH | 003 | 100-CH-003 | Chute | Grizzly Feeder Discharge Chute |  | Proton |  |  |  | 0
100 | CR | 001 | 100-CR-001 | Crusher | Jaw Crusher | Metso Outotec | Chemitec/Metso Outotec | C 106 Series |  |  | 110 |  | X | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 MCC & 1 PLC for Crushing Unit (Greezly Feeder & Crusher) is included in Vendor Scope.
100 | CH | 004 | 100-CH-004 | Chute | Jaw Crusher Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 001 | 100-CV-001 | Belt Conveyor | Conveyor 1 | Birikim | Birikim | 5° slope |  |  | 4 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 005 | 100-CH-005 | Chute | Conveyor 1 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CV | 002 | 100-CV-002 | Belt Conveyor | Conveyor 2 | Birikim | Birikim | 10° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
100 | WT | 001 | 100-WT-001 | Weightometer | Weightometer | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 006 | 100-CH-006 | Chute | Conveyor 2 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | DM | 001 | 100-ST-001 | Storage | Crushed Ore Storage |  | Proton |  |  |  | 0
100 | CH | 007 | 100-CH-007 | Chute | Apron Feeder Feed 1 Chute |  | Proton |  |  |  | 0
100 | CH | 008 | 100-CH-008 | Chute | Apron Feeder Feed 2 Chute |  | Proton |  |  |  | 0
100 | CH | 009 | 100-CH-009 | Chute | Apron Feeder Feed 3 Chute |  | Proton |  |  |  | 0
100 | AF | 001 | 100-AF-001 | Apron feeder | Apron Feeder 1 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | AF | 002 | 100-AF-002 | Apron feeder | Apron Feeder 2 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 set of PLC for 3 Apron Feeders is included in Vendor Scope.
100 | AF | 003 | 100-AF-003 | Apron feeder | Apron Feeder 3 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | CH | 010 | 100-CH-010 | Chute | Apron Feeder 1 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 011 | 100-CH-011 | Chute | Apron Feeder 2 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 012 | 100-CH-012 | Chute | Apron Feeder 3 Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 003 | 100-CV-003 | Dribble chute | Conveyor 3 | Birikim | Birikim | 0° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 013 | 100-CH-013 | Chute | Conveyor 3 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CH | 014 | 100-CH-014 | Chute | Apron Feeder 1 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 015 | 100-CH-015 | Chute | Apron Feeder 2 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 016 | 100-CH-016 | Chute | Apron Feeder 3 Fines Chute |  | Proton |  |  |  | 0
100 | DC | 001 | 100-DC-001 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 1.1 |  |  |  | Birikim Offer #211314_R5
100 | FA | 001 | 100-FA-001 | Fan | Dust Collector Fan | Birikim | Birikim | AL-RS1N-B 500 |  |  | 22 |  |  |  | Birikim Offer #211314_R5
100 | RV | 001 | 100-RV-001 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | DC | 002 | 100-DC-002 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 2.2 |  |  |  | Birikim Offer #211314_R5
100 | FA | 002 | 100-FA-002 | Fan | Dust Collector Fan | Birikim | Birikim |  |  |  | 45 |  |  |  | Birikim Offer #211314_R5
100 | RV | 002 | 100-RV-002 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | CN | 001 | 100-CN-001 | Overhead crane | Overhead crane |  | Chemitec/Supplier |  | X | X | 44 |  |  |  | Estimate based on highest power from vendor
100 | MA | 001 | 100-MA-001 | Self cleaning magnet | Self cleaning magnet | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 017 | 100-CH-017 | Chute | Scrap Chute |  | Proton |  |  |  | 0
100 | SP | 001 | 100-SP-001 | SUMP PUMP | Portable Sump Pump Crushing Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
100 | SP | 002 | 100-SP-002 | SUMP PUMP | Portable Sump Pump Stockpile Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 15 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
200 | CV | 1 | 200-CV-001 | Belt conveyor | CONVEYOR | Birikim | Birikim | 13° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 1 | 200-CH-001 | Chute | CONVEYOR DISCHARGE CHUTE | Birikim | Birikim |  |  |  | 0
200 | CV | 2 | 200-CV-002 | Belt conveyor | CONVEYOR | Birikim | Birikim | 10° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | CV | 3 | 200-CV-003 | Belt conveyor | CONVEYOR | Birikim | Birikim | 6° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | MA | 1 | 200-MA-001 | Self cleaning magnet | SELF CLEANING MAGNET | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 1 | 200-WT-001 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 2 | 200-WT-002 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 2 | 200-CH-002 | Chute | SAG MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | SM | 1 | 200-SM-001 | SAG Mill | SAG MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø5.00 m X 2.50 m EGL SAG Mill |  | X | 1044.516 |  |  |  | Power: C.008312-EE-YRK-DWG-00032-01_900113292. MCC & PLC: 3067739 - RMG Beqtaqari- MO Select 5.0 m x 2.5 m EGL SAG Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 Low voltage MCC & 1 PLC for SAG Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 1 | 200-TR-001 | Mill Trommel | SAG MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | JS | 1 | 200-JS-001 | Jacking system | MILL JACKING SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
200 | LN | 1 | 200-LN-001 | Liner Handler | SAG MILL LINER HANDLER | Russell | Chemitec/Supplier |  |  |  | 30 |  |  |  | Russel Offer: Q034634 BEQTAQARI - R3-1000 LINER HANDLER - RAILED 20220302 130353
200 | CH | 3 | 200-CH-003 | Chute | SAG MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | CH | 4 | 200-CH-004 | Chute | SAG MILL REJECT CHUTE |  | Proton |  |  |  | 0
200 | CH | 5 | 200-CH-005 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | CH | 6 | 200-CH-006 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | HP | 1 | 200-BX-001 | Distribution launder | DISTRIBUTION LAUNDER |  | Proton |  |  |  | 0
200 | PB | 1 | 200-PB-001 | Pump Box | PRIMARY PUMP BOX |  | Proton |  |  |  | 0
200 | PP | 1 | 200-PP-001 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | PP | 2 | 200-PP-002 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | CY | 1 | 200-CY-001 | Hydrocyclone | BALL MILL CYCLONE 1 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CY | 2 | 200-CY-002 | Hydrocyclone | BALL MILL CYCLONE 2 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CH | 7 | 200-CH-007 | Chute | BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | BM | 1 | 200-BM-001 | Ball Mill | BALL MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø3.40 m X 5.95 m EGL Ball Mill |  |  | 996.716 |  | X | X | Power: C.008312-EE-YRK-DWG-00040-02_900113293, MCC &PLC: 3067739 - RMG Beqtaqari - MO Select 3.4 m x 5.95 m EGL Ball Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 LW MCC & 1 PLC for Ball Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 2 | 200-TR-002 | Mill Trommel | BALL MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | CH | 8 | 200-CH-008 | Chute | BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | PT | 1 | 200-PT-001 | Scats Hopper | SCATS HOPPER |  | Proton |  |  |  | 0
200 | BN | 1 | 200-BN-001 | Ball pits | BALL PIT | RMG | Chemitec |  |  |  | 0
200 | MA | 1 | 200-MA-001 | Ball magnet | BALL MAGNET |  | Supplier |  |  |  | TBD |  |  |  | RMG to provide power
200 | BB | 1 | 200-BB-001 | Ball bucket | BALL BUCKET |  | Supplier |  |  |  | 0
200 | CH | 9 | 200-CH-009 | Chute | BALL CHARGER CHUTE |  | Supplier |  |  |  | 0
200 | CN | 1 | 200-CN-001 | Overhead crane | GRINDING AREA OVERHEAD CRANE |  | Chemitec |  | X | X | 60.4 |  |  |  |  | Preliminary power estimated by highest consumer offered
200 | BX | 4 | 200-BX-004 | Pebbles Box | PEBBLES BOX |  | Proton |  |  |  | 0 |  |  |  |  | Added 16.8.2022
200 | SP | 1 | 200-SP-001 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 2 | 200-SP-002 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 3 | 200-SP-003 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
300 | SA | 1 | 300-SA-001/2 | Process Sampler | FLOTATION FEED (LSA SAMPLER (PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 1 | 300-SV-001/2 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-001/2 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 1 | 300-SA-001/1 | Metallurgical Sampler | FLOTATION FEED (MSA SAMPLER (EA)) | Metso Outotec | Chemitec |  |  |  | 15
300 | TK | 1 | 300-TK-001 | Tank | BULK ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
300 | AG | 1 | 300-AG-001 | AGITATOR | AGITATOR FOR BULK CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 15 |  |  |  | Offer SPX : 30966,30977
300 | FC | 1 | 300-FC-001 | Flotation Cell | BULK ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 2 | 300-FC-002 | Flotation Cell | BULK ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 3 | 300-FC-003 | Flotation Cell | BULK ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 4 | 300-FC-004 | Flotation Cell | BULK ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 5 | 300-FC-005 | Flotation Cell | BULK ROUGHER CELL 5 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 6 | 300-FC-006 | Flotation Cell | BULK SCAVENGER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 7 | 300-FC-007 | Flotation Cell | BULK SCAVENGER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | CH | 3 | 300-CH-003 | Launder | CELLS 001-005 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | CH | 4 | 300-CH-004 | Launder | CELLS 006-007 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 4 | 300-PB-004 | Pump Box | BULK ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 9 | 300-PP-009 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 10 | 300-PP-010 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PB | 3 | 300-PB-003 | Pump Box | BULK SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 7 | 300-PP-007 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 8 | 300-PP-008 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 3 | 300-SA-003 | Process Sampler | BULK SCAVENGER CONCENTARET (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
300 | SV | 3 | 300-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | PB | 1 | 300-PB-001 | Pump Box | SCAVENGER TAILING PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 3 | 300-PP-003 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 4 | 300-PP-004 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 2 | 300-SA-002 | Metallurgical Sampler | BULK SCAVENGER TAILINGS (MSA SAMPLER (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
300 | CY | 1 | 300-CY-001 | Hydrocyclone | REGRIND CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | CY | 2 | 300-CY-002 | Hydrocyclone | REGRIND CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | BX | 1 | 300-BX-001 | Distribution Box | DISTRIBUTION BOX 1 |  | Proton |  |  |  | 0
300 | CH | 1 | 300-CH-001 | Chute | REGRIND BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
300 | BM | 1 | 300-BM-001 | Ball Mill | REGRIND BALL MILL | CEMTEC | Chemitec/CEMTEC | Wet Ball Mill Ø2.40 m X 3.75 m |  |  | 254.61 |  |  | X | 208206-740-100-MBM-ELA001-00, Appendix 1_A113245-05_commercial_offer_ball_mill | Power includes auxiliaries
300 | TR | 1 | 300-TR-001 | Mill Trommel | REGRIND BALL MILL TROMMEL | CEMTEC | CEMTEC |  |  |  | 0
300 | CH | 1 | 300-CH-002 | Chute | REGRIND BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 2 | 300-PB-002 | Pump Box | REGRIND CYCLONE FEED PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 5 | 300-PP-005 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 6 | 300-PP-006 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 5 | 300-SA-005 | Process Sampler | Pb ROUGHER FEED-GOING TO Zn COND.(LSA SAMPLER (EA&PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 5 | 300-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 4 | 300-SA-004 | Process Sampler | Pb ROUGHER FEED-LSA SAMPLER (EA&PSD) |  | Chemitec |  |  |  | 0
300 | SV | 4 | 300-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | CN | 1 | 300-CN-001 | Overhead Crane | BULK FLOTATION AND REGRINDING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
300 | SP | 1 | 300-SP-001 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 2 | 300-SP-002 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 3 | 300-SP-003 | SUMP PUMP | SUMP PUMP REGRINDING BALL MILL | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | ES | 1 | 300-ES-001 | Emergency Station | EMERGENCY SHOWER & EYE WASH STATION |  | Proton |  |  |  | 0
305 | TK | 1 | 305-TK-001 | TANK | TAILINGS THICKENER FEED TANK |  | Chemitec/Proton | 4 m3 |  |  | 0
305 | RA | 1 | 305-RA-001 | RAKE MECHANISM | TAILINGS THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 4 |  |  |  | 3274949 Technical Description rev.06
305 | TH | 1 | 305-TH-001 | THICKENER | TAILINGS THICKENER | Metso Outotec | Chemitec | HRT - 16 m | X |  | 1.5 |  |  |  | OU500759567_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
305 | PP | 1 | 305-PP-001 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 2 | 305-PP-002 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | TK | 2 | 305-TK-002 | TANK | TAILINGS FILTER FEED SURGE TANK |  | Chemitec/Proton | 250 m3 |  |  | 0
305 | AG | 2 | 305-AG-002 | AGITATOR | AGITATOR FOR TAILINGS FILTER FEED SURGE TANK |  | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
305 | PP | 5 | 305-PP-005 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 6 | 305-PP-006 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | FL | 1 | 305-FL-001 | FILTER PRESS | TAILINGS FILTER | Diemme | Chemitec/Diemme | ME 2000 F15 |  |  | 49.62 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Bulk Tailings Filter Press is included in Vendor Scope.
305 | PB | 2 | 305-PB-002 | PUMP BOX | TAILINGS THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 8 | 305-PP-008 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | CH | 1 | 305-CH-001 | CHUTE | TAILINGS PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
305 | CV | 1 | 305-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-1000 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 2 | 305-CV-002 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | XE400 2+2 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 3 | 305-CV-003 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125, 2+2 |  |  | 11 |  |  |  | Birikim Offer # 211600 R2
305 | BN | 1 | 305-BN-001 | TAILINGS SILO | TAILINGS SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
305 | CN | 1 | 305-CN-001 | OVERHEAD CRANE | TAILINGS DEWATERING OVERHAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
305 | SP | 1 | 305-SP-001 | SUMP PUMP | SUMP PUMP FOR TAILINGS THICKENER AREA | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 2 | 305-SP-002 | SUMP PUMP | SUMP PUMP FOR TAILINGS FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 3 | 305-SP-003 | SUMP PUMP | FILTER WASHING AND RINSING WASHING SUMP PUMP | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | TK | 4 | 305-TK-004 | TANK | FILTER WASHING WATER TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 200 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | P&ID shows 137 kW. (MH: 137 might me working power)
305 | PP | 8 | 305-PP-008 | PUMP | HIGH PRESSURE WASHING PUMP | Diemme | Diemme | Piston type pump |  | X | 37 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
310 | TK | 1 | 310-TK-001 | Tank | Pb ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-001 | AGITATOR | AGITATOR FOR Pb CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | FC | 1 | 310-FC-001 | Flotation Cell | Pb ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 2 | 310-FC-002 | Flotation Cell | Pb ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 3 | 310-FC-003 | Flotation Cell | Pb ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 4 | 310-FC-004 | Flotation Cell | Pb ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 5 | 310-FC-005 | Flotation Cell | Pb SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | PB | 1 | 310-PB-001 | Pump Box | DEWATERING CYCLONES FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 1 | 310-PP-001 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 2 | 310-PP-002 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 8 | 310-PB-008 | Pump Box | Pb SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 17 | 310-PP-017 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 18 | 310-PP-018 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | CY | 1 | 310-CY-001 | Hydrocyclone | DEWATERING CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | CY | 2 | 310-CY-002 | Hydrocyclone | DEWATERING CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | HP | 1 | 310-HP-001 | Grinding Media Addition System | MEDIA ADDITION SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
310 | BN | 1 | 310-BN-001 | Bin | MEDIA HANDLING BIN | Metso Outotec | Metso Outotec |  |  |  | 0
310 | HP | 1 | 310-HP-001 | Hopper | MEDIA HOPPER | Metso Outotec | Metso Outotec |  |  |  | 0
310 | SD | 1 | 310-SD-001 | Mill | FINE GRIND MILL | Metso Outotec | Metso Outotec | SMD-E-90 |  |  | 92.41 |  |  |  | C.008574-EE-YRK-DWG-00030 | Including auxiliary equipment
310 | PB | 2 | 310-PB-002 | Pump Box | Pb 1st CLEANER FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 3 | 310-PP-003 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 4 | 310-PP-004 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 2 | 310-SA-002 | Process Sampler | Pb ROUGHER CONCENTRATE (ASA SAMPLER (EA & PSD)) |  | Chemitec |  |  |  | 0
310 | SV | 6 | 310-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SV | 2 | 310-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | TK | 2 | 310-TK-002 | Tank | Pb 1st CLEANER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-002 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 1 | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | TK | 3 | 310-TK-003 | Tank | Pb 1st CLEANER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 3 | 310-AG-003 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 2 | SPX Flow | Supplier |  | X |  | 3 |  |  |  | Offer SPX : 30966,30977
310 | FC | 6 | 310-FC-006 | Flotation Cell | Pb 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 7 | 310-FC-007 | Flotation Cell | Pb 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 8 | 310-FC-008 | Flotation Cell | Pb 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | SA | 4 | 310-SA-004 | Process Sampler | Pb 1st CLEANER TAILING (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 4 | 310-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 3 | 310-PB-003 | Pump Box | Pb 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 5 | 310-PP-005 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 6 | 310-PP-006 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 9 | 310-FC-009 | Flotation Cell | Pb 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 10 | 310-FC-010 | Flotation Cell | Pb 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | PB | 4 | 310-PB-004 | Pump Box | Pb 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 7 | 310-PP-007 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 8 | 310-PP-008 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 9 | 310-PB-009 | Pump Box | Pb 2nd CLEANER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 19 | 310-PP-019 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 20 | 310-PP-020 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 5 | 310-SA-005 | Process Sampler | Pb 2nd CLEANER CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 5 | 310-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | FC | 11 | 310-FC-011 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 12 | 310-FC-012 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 13 | 310-FC-013 | Flotation Cell | Pb 3rd CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | SA | 6 | 310-SA-006 | Process Sampler | Pb 3rd CLEANER TAILINGS (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | PB | 5 | 310-PB-005 | Pump Box | Pb 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 9 | 310-PP-009 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 10 | 310-PP-010 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 14 | 310-FC-014 | Flotation Cell | Pb 4th CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 15 | 310-FC-015 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 16 | 310-FC-016 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | PB | 6 | 310-PB-006 | Pump Box | Pb 4th CLEANER CONC. PUMP BOX |  | Chemitec |  |  | X | 0
310 | PP | 11 | 310-PP-011 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 12 | 310-PP-012 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 1 | 310-SA-001 | Metallurgical Sampler | Pb FINAL CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 1 | 310-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 10 | 310-PB-010 | Pump Box | Pb TAILINGS DISCHARGE PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 13 | 310-PP-013 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 14 | 310-PP-014 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 3 | 310-SA-003 | Process Sampler | Pb TAILINGS (PSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 3 | 310-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SP | 1 | 310-SP-001 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 2 | 310-SP-002 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 3 | 310-SP-003 | SUMP PUMP | SUMP PUMP FINE GRINDING MILL | Metso Outotec | Metso Outotec / Chemitec | VS25 L80 O5D85 HC | X | X | 2.2 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | CH | 1 | 310-CH-001 | Launder | Pb Rougher Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 2 | 310-CH-002 | Launder | Pb Rougher Scav Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 3 | 310-CH-003 | Launder | Pb 1st cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 4 | 310-CH-004 | Launder | Pb 2nd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 5 | 310-CH-005 | Launder | Pb 3rd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 6 | 310-CH-006 | Launder | Pb 4th cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | TK | 1 | 320-TK-001 | Tank | Zn ROUGHER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 1 | 320-AG-001 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 1 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | TK | 2 | 320-TK-002 | Tank | Zn ROUGHER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 2 | 320-AG-002 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 2 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | FC | 1 | 320-FC-001 | Flotation Cell | Zn ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 2 | 320-FC-002 | Flotation Cell | Zn ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 3 | 320-FC-003 | Flotation Cell | Zn ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 4 | 320-FC-004 | Flotation Cell | Zn SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | PB | 1 | 320-PB-001 | Pump Box | Zn ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 1 | 320-PP-001 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 2 | 320-PP-002 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 1 | 320-SA-001 | Process Sampler | Zn ROUGHER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 1 | 320-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SA | 7 | 320-SA-007 | Process Sampler | Zn ROUGHER SCAVENGER TAILINGS (LSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 7 | 320-SV-007 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-007 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 7 | 320-PB-007 | Pump Box | Zn SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 13 | 320-PP-013 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 14 | 320-PP-014 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 2 | 320-PB-002 | Pump Box | Zn ROUGHER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 3 | 320-PP-003 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 4 | 320-PP-004 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 3 | 320-SA-003 | Metallurgical Sampler | Zn TAILINGS (MSA Sampler (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
320 | FC | 5 | 320-FC-005 | Flotation Cell | Zn 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 6 | 320-FC-006 | Flotation Cell | Zn 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 7 | 320-FC-007 | Flotation Cell | Zn 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 8 | 320-FC-008 | Flotation Cell | Zn 1st CLEANER SCAVENGER CELL | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 2 | 320-SA-002 | Process Sampler | Zn 1st CLEANER-SCAVENGER TAILINGS (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 2 | 320-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 6 | 320-PB-006 | Pump Box | Zn 1st CLEANER SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 11 | 320-PP-011 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 12 | 320-PP-012 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 3 | 320-PB-003 | Pump Box | Zn 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 5 | 320-PP-005 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 6 | 320-PP-006 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 5 | 320-SA-005 | Process Sampler | Zn 1st CLEANER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 5 | 320-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | FC | 9 | 320-FC-009 | Flotation Cell | Zn 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 10 | 320-FC-010 | Flotation Cell | Zn 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 6 | 320-SA-006 | Process Sampler | Zn 2nd CLANER TAILINGS (ADAPTED RD SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 6 | 320-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 4 | 320-PB-004 | Pump Box | Zn 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 7 | 320-PP-007 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5. |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 8 | 320-PP-008 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | FC | 11 | 320-FC-011 | Flotation Cell | Zn 3rd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 12 | 320-FC-012 | Flotation Cell | Zn 3rd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | PB | 5 | 320-PB-005 | Pump Box | Zn 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 9 | 320-PP-009 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 10 | 320-PP-010 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 15 | 320-PP-015 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 16 | 320-PP-016 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 4 | 320-SA-004 | Metallurgical Sampler | Zn FINAL CONCENTRATE- RD SAMPLER (EA) |  | Chemitec |  |  |  | 0
320 | SV | 4 | 320-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SP | 1 | 320-SP-001 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | SP | 2 | 320-SP-002 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | CH | 1 | 320-CH-001 | Launder | Zn Rougher Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 2 | 320-CH-002 | Launder | Zn Rougher Scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 3 | 320-CH-003 | Launder | Zn 1st cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 4 | 320-CH-004 | Launder | Zn 1st cl scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 5 | 320-CH-005 | Launder | Zn 2nd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 6 | 320-CH-006 | Launder | Zn 3rd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
325 | RA | 1 | 325-RA-001 | RAKE MECHANISM | Zn TAILINGS THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 5.5 |  |  |  | 3274949 Technical Description rev.06
325 | TH | 1 | 325-TH-001 | THICKENER | Zn TAILINGS THICKENER | Metso Outotec | Chemitec | HCT - 12 m | X |  | 1.5 |  |  |  | OU500759580_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
325 | PP | 1 | 325-PP-001 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 2 | 325-PP-002 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | AG | 2 | 325-AG-002 | AGITATOR | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
325 | PP | 5 | 325-PP-005 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 6 | 325-PP-006 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | FL | 1 | 325-FL-001 | FILTER PRESS | Zn TAILINGS FILTER | Diemme | Chemitec/Diemme | ME 2000 F13 |  |  | 49.62 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Zn Tailings Filter Press is included in Vendor Scope.
325 | PP | 7 | 325-PP-007 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 8 | 325-PP-008 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | CV | 1 | 325-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-630 |  |  | 9.2 |  |  |  | Birikim Offer # 211600 R2
325 | CV | 2 | 325-CV-002 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
325 | SP | 1 | 325-SP-001 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS THICKENER AREA | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Will be updated with MOs next rpoposal
325 | SP | 2 | 325-SP-002 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS FILTER FEED TANK AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
325 | SP | 3 | 325-SP-003 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
325 | PP | 9 | 325-PP-009 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 160 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | P&ID shows 132 kW (might be working power)
325 | PP | 10 | 325-PP-010 | PUMP | HIGH PRESSURE WASHING PUMP | Diemme | Diemme | Piston type pump |  | X | 37 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
400 | TK | 1 | 400-TK-001 | TANK | Pb CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 1 | 400-RA-001 | RAKE MECHANISM | Pb CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 1 | 400-TH-001 | THICKENER | Pb CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759542_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 1 | 400-PP-001 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 2 | 400-PP-002 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PB | 1 | 400-PB-001 | PUMP BOX | Pb CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 3 | 400-PP-003 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 4 | 400-PP-004 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 2 | 400-TK-002 | TANK | Pb CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 2 | 400-AG-002 | AGITATOR | AGITATOR FOR Pb CONCENTRATE FEED SURGE TANK |  | SPX Flow | SPX Flow | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 5 | 400-PP-005 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 6 | 400-PP-006 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 1 | 400-FL-001 | FILTER PRESS | Pb CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.1500 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Pb Concentrate Filter Press is included in Vendor Scope.
400 | PB | 1 | 400-PB-003 | PUMP BOX | Pb CONCENTRATE FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 7 | 400-PP-007 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 8 | 400-PP-008 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 1 | 400-CH-001 | CHUTE | Pb CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 1 | 400-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 1 | 400-SA-001 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 2 | 400-CV-002 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 1 | 400-BN-001 | TAILINGS SILO | Pb CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 1 | 400-FE-001 | SCREW EXTRACTOR | Pb CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 1 | 400-BS-001 | BAGGING SYSTEM | Pb CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | SP | 1 | 400-SP-001 | SUMP PUMP | SUMP PUMP FOR Pb CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC |  | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Tag changed. 3.8.2022
400 | PP | 18 | 400-PP-018 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 9.2 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | NOTE CHANGED TAG
400 | TK | 3 | 400-TK-003 | TANK | Zn CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 2 | 400-RA-002 | RAKE MECHANISM | Zn CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 2 | 400-TH-002 | THICKENER | Zn CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759554_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 9 | 400-PP-009 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PP | 10 | 400-PP-010 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PB | 2 | 400-PB-002 | PUMP BOX | Zn CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 11 | 400-PP-011 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 12 | 400-PP-012 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 4 | 400-TK-004 | TANK | Zn CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 4 | 400-AG-004 | AGITATOR | AGITATOR FOR Zn CONCENTRATE FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 13 | 400-PP-013 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 14 | 400-PP-014 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 2 | 400-FL-002 | FILTER PRESS | Zn CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.2700 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Zn Concentrate Filter Press is included in Vendor Scope.
400 | PB | 4 | 400-PB-004 | PUMP BOX | Zn CONCENTRATE THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 15 | 400-PP-015 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 16 | 400-PP-016 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 2 | 400-CH-002 | CHUTE | Zn CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 3 | 400-CV-003 | BELT CONVEYOR | CONVEYOR | Supplier | Supplier | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 2 | 400-SA-002 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 4 | 400-CV-004 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 2 | 400-BN-002 | TAILINGS SILO | Zn CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 2 | 400-FE-002 | SCREW EXTRACTOR | Zn CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 2 | 400-BS-002 | BAGGING SYSTEM | Zn CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | CN | 1 | 400-CN-001 | OVERHEAD CRANE | CONCENTRATE DEWATERING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
400 | PP | 17 | 400-PP-017 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 11 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
400 | SP | 2 | 400-SP-002 | SUMP PUMP | SUMP PUMP FOR Zn CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Added 4.8.2022.
500 | XX | 1 | 500-XX-001 | REAGENT MIXING AND DOSING | MIBC MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.4 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 2 | 500-XX-002 | REAGENT MIXING AND DOSING | AERO 208 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.45 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 3 | 500-XX-003 | REAGENT MIXING AND DOSING | W31 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.18 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 4 | 500-XX-004 | REAGENT MIXING AND DOSING | SODA ASH MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 10.65 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 5 | 500-XX-005 | REAGENT MIXING AND DOSING | Ca(OH)2 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 8.25 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 6 | 500-XX-006 | REAGENT MIXING AND DOSING | DEP347 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.12 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 7 | 500-XX-007 | REAGENT MIXING AND DOSING | ZnSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.23 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 8 | 500-XX-008 | REAGENT MIXING AND DOSING | CuSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 9 | 500-XX-009 | REAGENT MIXING AND DOSING | NaCN MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11.6 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 10 | 500-XX-010 | REAGENT MIXING AND DOSING | SIPX MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 11 | 500-XX-011 | REAGENT MIXING AND DOSING | Magnafloc 1687 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.62 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 12 | 500-XX-012 | REAGENT MIXING AND DOSING | Magnafloc 10 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 3.34 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 13 | 500-XX-013 | REAGENT MIXING AND DOSING | Magnafloc 333 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | SP | 1 | 500-SP-001 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 2 | 500-SP-002 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 3 | 500-SP-003 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 2 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 4 | 500-SP-004 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 3 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 5 | 500-SP-005 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 4 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
600 | CP | 1 | 600-CP-001 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 2 | 600-CP-002 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 |  |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 3 | 600-CP-003 | AIR COMPRESSOR | PLANT AIR COMPRESSOR - STAND BY | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | AR | 1 | 600-AR-001 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AR | 2 | 600-AR-002 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AD | 1 | 600-AD-001 | AIR DRYER | INSTRUMENT AIR DRYER | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0
600 | AD | 2 | 600-AD-002 | AIR DRYER | INSTRUMENT AIR DRYER-STAND BY | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0 | X
600 | AR | 5 | 600-AR-005 | AIR RECEIVER | INSTRUMENT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 10 m3 |  |  | 0
600 | BL | 1 | 600-BL-001 | AIR BLOWER | FLOTATION AIR BLOWER |  | Continental/Chemitec |  |  |  | 160 |  |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | BL | 2 | 600-BL-002 | AIR BLOWER | FLOTATION AIR BLOWER - STAND BY |  | Continental/Chemitec |  |  |  | 160 | X |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | FL | 1 | 600-IF-001 | INLET FILTER | INLET FILTER FOR AIR BLOWER |  | Continental/Chemitec |  |  |  | 0
600 | FL | 2 | 600-IF-002 | INLET FILTER | INLET FILTER FOR AIR BLOWER-STAND BY |  | Continental/Chemitec |  |  |  | 0 | X
600 | CP | 4 | 600-CP-004 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 5 | 600-CP-005 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 6 | 600-CP-006 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | CP | 7 | 600-CP-007 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-5
600 | CP | 8 | 600-CP-008 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-6
600 | CP | 9 | 600-CP-009 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-7
600 | AR | 3 | 600-AR-003 | AIR RECEIVER | FILTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | AR | 4 | 600-AR-004 | AIR RECEIVER | FLTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | TK | 1 | 600-TK-001 | WATER TANK | PROCESS WATER TANK BULK FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 1 | 600-PP-001 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 2 | 600-PP-002 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 2 | 600-TK-002 | WATER TANK | PROCESS WATER TANK Pb FLOTATION |  |  | 30 m3 |  |  | 0
600 | PP | 3 | 600-PP-003 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 4 | 600-PP-004 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 3 | 600-TK-003 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | TK | 4 | 600-TK-004 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 5 | 600-PP-005 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 6 | 600-PP-006 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 5 | 600-TK-005 | WATER TANK | PROCESS WATER TANK BLEEDING TANK |  |  | 20 m3 |  |  | 0
600 | PP | 7 | 600-PP-007 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 8 | 600-PP-008 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 6 | 600-TK-006 | WATER TANK | FRESH WATER TANK |  |  | 300 m3 |  |  | 0
600 | PP | 9 | 600-PP-009 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 10 | 600-PP-010 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 11 | 600-PP-011 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 12 | 600-PP-012 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 7 | 600-TK-007 | WATER TANK | FIRE WATER TANK |  |  | 150 m3 |  |  | 0 |  |  |  | 1. Fire extinguishing system - 380V, 50Hz, 37kW, 97.3 A;
600 | PP | 13 | 600-PP-013 | PUMP | FIRE WATER PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 2. Alarm system - 220V, 500 Watt, 2,3 A; | Information given by RMG on 5.9.2022
600 | PP | 14 | 600-PP-014 | PUMP | FIRE WATER JOCKEY PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 3. Emergency lighting - 220V, 22.4 kW, 100.1 A;
600 | PP | 15 | 600-PP-015 | PUMP | FIRE WATER DIESEL PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 4. Emergency alarm/sirens - 220V, 500 Watt, 2.3A.
600 | SP | 1 | 600-SP-001 | SUMP PUMP | SUMP PUMP Zn-Pb PROCESS WATER TANKS | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 4 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
600 | SP | 2 | 600-SP-002 | SUMP PUMP | SUMP PUMP Zn-Pb TAILINGS, BULK & FRESH WATER TANKS AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
700 | PA | 1 | 700-PA-001 | PARTICLE SIZE ANALYSER | PARTICLE SIZE ANALYSER | Metso Outotec | Chemitec |  |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 4 | 700-MP-004 | MULTIPLEXER | PARTICLE SIZE ANALYSER MULTIPLEXER | Metso Outotec | Chemitec |  |  |  | 0
700 | TK | 1 | 700-TK-001 | TANK | DILUTION WATER TANK | Metso Outotec | Chemitec |  |  |  | 0
700 | EA | 1 | 700-EA-001 | ELEMENTAL ANALYSER | ELEMENTAL ANALYSER | Metso Outotec | Chemitec |  |  |  | 1.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 1 | 700-PP-001 | PUMP | SAMPLE TRANSFER PUMP MXA 1 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 2 | 700-PP-002 | PUMP | SAMPLE TRANSFER PUMP MXA 2 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 4 | 700-PP-004 | PUMP | SAMPLE TRANSFER PUMP PSA - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 1 | 700-MP-001 | MULTIPLEXER | EA MULTIPLEXER 1 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 2 | 700-MP-002 | MULTIPLEXER | EA MULTIPLEXER 2 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 3 | 700-MP-003 | MULTIPLEXER | EA MULTIPLEXER 3 | Metso Outotec | Chemitec |  |  |  | 0
700 | PV | 1 | 700-VP-001 | VERTICAL PUMP | SAMPLE RETURN PUMP 1 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 2 | 700-VP-002 | VERTICAL PUMP | SAMPLE RETURN PUMP 2 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 3 | 700-VP-003 | VERTICAL PUMP | SAMPLE RETURN PUMP 3 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 4 | 700-VP-004 | VERTICAL PUMP | SAMPLE RETURN PUMP 4 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PB | 1 | 700-PB-001 | PUMP BOX | Pb Final Conc. Pump box | [5 empty] | 0
700 | PP | 5 | 700-PP-005 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 6 | 700-PP-006 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 8 | 700-PP-008 | PUMP | DILUTION WATER PUMP | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 3 | 700-PP-003 | PUMP | SAMPLE TRANSFER PUMP MXA 3 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 7 | 700-PP-007 | PUMP | SAMPLE TRANSFER VERTICAL PUMP | Metso Outotec |  | VF50 |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | DP | 1 | 700-DP-001 | DEMULTIPLEXER | DEMULTIPLEXER | Metso Outotec |  |  |  |  | 0 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
999 |  |  |  | Lighting - Main building |  |  |  |  | X |  | 20 |  |  |  | RMG Email from 6.9.2022 | 1. Reserve cells/sections in MCCs – We would prefer to reserve 1 free cell in MCCs for each location (crusher and main building MCCs) with 50kW in order to have spare capacity for connecting additional HVAC, water mist sprayers at ore pad, other equipment.
999 |  |  |  | HVAC - Crusher building |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Stockpile |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Main building |  |  |  |  | X |  | 70
999 |  |  |  | AC for transfromer and MCC room |  |  |  |  | X |  | 50
Note on J137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should not be necessary to use, but could be good to have the option.
Note on J219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can send it to the Zn RF or the Bulk RF as long as the valves in the split are energized.
Note on J296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Energize pumps, so we can feed soda ash to the NaCN if needed. Also electrical sockets for the portable sump pumps.
Note on J368: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. pH measurement, Fan for gases and fumes and sump pump
Note on J369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. Fan for gases and fumes and sump pump
Note on J371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electrical sockets for the portable sump pumps.

## Tanks
Tank Application | Number of tanks | Tank capacity, m3 | Inner lining | Temperature of the process,C | Outlet flange diameter DN, mm | ASME pressure class
Feed tank | 1 | 31,6 | + | 45 | 600 | CL 150
Overflow tank | 1 | 918 | + | 30 | 600 | CL 150
Underflow tank (with agitator) | 1 | 182 | + | 30 | 300 | CL 150
Gland seal water tank | 1 | 60 | + | 30 | 80 | CL 400
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.

## К приобретению для селекции (hidden)
|  |  |  | Customer | JSC RMG Auramine LLC |  |  |  | By | Date
|  |  |  | Project Name | Beqtaqari Detailed Engineering |  |  | Prepared | MHA | 23/05/2022
|  |  |  | Project Number | P1384 |  |  | Checked | LRU | 2022-10-28
|  |  |  | Document Name | Equipment List |  |  | Released | ESA | 2022-09-26
|  |  |  | Document Number | P1384-000-PR-001-8
|  |  |  | Revision | 8
NO ZONE | DESCR. | #ITEM | EQUIPMENT TAG | Equipment Description | Equipment Name | Supply by | Equipment sizing done by | Model | Critical Load | VFD | POWER, kW Installed | Stby | MCC | PLC | INFORMATION SOURCE | Comments
100 | SC | 001 | 100-SC-001 | Screen | Static grizzly screen |  | Chemitec/Proton | Opening size: 560 mm |  |  | 0
100 | HP | 001 | 100-HP-001 | Hopper | Hopper |  | Chemitec/Proton | Volume 50 m3 |  |  | 0
100 | CH | 001 | 100-CH-001 | Chute | Grizzly Feeder Feed Chute |  | Proton |  |  |  | 0
100 | GF | 001 | 100-FE-001 | Grizzly Feeder | Grizzly Feeder | Metso Outotec | Chemitec/Metso Outotec | TKF11-42-2V |  | X | 12 |  | X | X | P202110.01-E01_MCC_PROJECT-Rev03 | Power has updated on 8.9.2022. Power is taken from Vendor-MCC Project document. Power includes auxilary equipment for Crushing Unit (Grizzly Feeder+ Jaw crusher), which is 2 kW
100 | CH | 002 | 100-CH-002 | Chute | Grizzly Feeder Fine Chute |  | Proton |  |  |  | 0
100 | CH | 003 | 100-CH-003 | Chute | Grizzly Feeder Discharge Chute |  | Proton |  |  |  | 0
100 | CR | 001 | 100-CR-001 | Crusher | Jaw Crusher | Metso Outotec | Chemitec/Metso Outotec | C 106 Series |  |  | 110 |  | X | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 MCC & 1 PLC for Crushing Unit (Greezly Feeder & Crusher) is included in Vendor Scope.
100 | CH | 004 | 100-CH-004 | Chute | Jaw Crusher Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 001 | 100-CV-001 | Belt Conveyor | Conveyor 1 | Birikim | Birikim | 5° slope |  |  | 4 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 005 | 100-CH-005 | Chute | Conveyor 1 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CV | 002 | 100-CV-002 | Belt Conveyor | Conveyor 2 | Birikim | Birikim | 10° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
100 | WT | 001 | 100-WT-001 | Weightometer | Weightometer | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 006 | 100-CH-006 | Chute | Conveyor 2 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | DM | 001 | 100-ST-001 | Storage | Crushed Ore Storage |  | Proton |  |  |  | 0
100 | CH | 007 | 100-CH-007 | Chute | Apron Feeder Feed 1 Chute |  | Proton |  |  |  | 0
100 | CH | 008 | 100-CH-008 | Chute | Apron Feeder Feed 2 Chute |  | Proton |  |  |  | 0
100 | CH | 009 | 100-CH-009 | Chute | Apron Feeder Feed 3 Chute |  | Proton |  |  |  | 0
100 | AF | 001 | 100-AF-001 | Apron feeder | Apron Feeder 1 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  | X | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | AF | 002 | 100-AF-002 | Apron feeder | Apron Feeder 2 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal | 1 set of PLC for 3 Apron Feeders is included in Vendor Scope.
100 | AF | 003 | 100-AF-003 | Apron feeder | Apron Feeder 3 | Metso Outotec | Chemitec/Metso Outotec | AF4-1219MN-3400-7.5KW-M RH |  | X | 7.5 |  |  |  | Appendix 1 - 3292053 RMG_Bolnisi Project Crushing Proposal
100 | CH | 010 | 100-CH-010 | Chute | Apron Feeder 1 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 011 | 100-CH-011 | Chute | Apron Feeder 2 Discharge Chute |  | Proton |  |  |  | 0
100 | CH | 012 | 100-CH-012 | Chute | Apron Feeder 3 Discharge Chute |  | Proton |  |  |  | 0
100 | CV | 003 | 100-CV-003 | Dribble chute | Conveyor 3 | Birikim | Birikim | 0° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 013 | 100-CH-013 | Chute | Conveyor 3 Discharge Chute | Birikim | Birikim |  |  |  | 0
100 | CH | 014 | 100-CH-014 | Chute | Apron Feeder 1 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 015 | 100-CH-015 | Chute | Apron Feeder 2 Fine Chute |  | Proton |  |  |  | 0
100 | CH | 016 | 100-CH-016 | Chute | Apron Feeder 3 Fines Chute |  | Proton |  |  |  | 0
100 | DC | 001 | 100-DC-001 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 1.1 |  |  |  | Birikim Offer #211314_R5
100 | FA | 001 | 100-FA-001 | Fan | Dust Collector Fan | Birikim | Birikim | AL-RS1N-B 500 |  |  | 22 |  |  |  | Birikim Offer #211314_R5
100 | RV | 001 | 100-RV-001 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | DC | 002 | 100-DC-002 | Dust collector | Dust Collector | Birikim | Birikim |  |  |  | 2.2 |  |  |  | Birikim Offer #211314_R5
100 | FA | 002 | 100-FA-002 | Fan | Dust Collector Fan | Birikim | Birikim |  |  |  | 45 |  |  |  | Birikim Offer #211314_R5
100 | RV | 002 | 100-RV-002 | Rotary valve | Rotary Valve | Birikim | Birikim |  |  |  | 0
100 | CN | 001 | 100-CN-001 | Overhead crane | Overhead crane |  | Chemitec/Supplier |  | X | X | 44 |  |  |  | Estimate based on highest power from vendor
100 | MA | 001 | 100-MA-001 | Self cleaning magnet | Self cleaning magnet | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
100 | CH | 017 | 100-CH-017 | Chute | Scrap Chute |  | Proton |  |  |  | 0
100 | SP | 001 | 100-SP-001 | SUMP PUMP | Portable Sump Pump Crushing Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
100 | SP | 002 | 100-SP-002 | SUMP PUMP | Portable Sump Pump Stockpile Area | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 15 | X |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Critical Load served by electrical socket in the location
200 | CV | 1 | 200-CV-001 | Belt conveyor | CONVEYOR | Birikim | Birikim | 13° slope |  |  | 15 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 1 | 200-CH-001 | Chute | CONVEYOR DISCHARGE CHUTE | Birikim | Birikim |  |  |  | 0
200 | CV | 2 | 200-CV-002 | Belt conveyor | CONVEYOR | Birikim | Birikim | 10° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | CV | 3 | 200-CV-003 | Belt conveyor | CONVEYOR | Birikim | Birikim | 6° slope |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | MA | 1 | 200-MA-001 | Self cleaning magnet | SELF CLEANING MAGNET | Birikim | Birikim | 600 Gauss at 250 mm |  |  | 2.2 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 1 | 200-WT-001 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | WT | 2 | 200-WT-002 | Weightometer | WEIGHTOMETER | Birikim | Birikim |  |  |  | 0 |  |  |  | Birikim Offer # 211169 R5
200 | CH | 2 | 200-CH-002 | Chute | SAG MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | SM | 1 | 200-SM-001 | SAG Mill | SAG MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø5.00 m X 2.50 m EGL SAG Mill |  | X | 1044.516 |  |  |  | Power: C.008312-EE-YRK-DWG-00032-01_900113292. MCC & PLC: 3067739 - RMG Beqtaqari- MO Select 5.0 m x 2.5 m EGL SAG Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 Low voltage MCC & 1 PLC for SAG Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 1 | 200-TR-001 | Mill Trommel | SAG MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | JS | 1 | 200-JS-001 | Jacking system | MILL JACKING SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
200 | LN | 1 | 200-LN-001 | Liner Handler | SAG MILL LINER HANDLER | Russell | Chemitec/Supplier |  |  |  | 30 |  |  |  | Russel Offer: Q034634 BEQTAQARI - R3-1000 LINER HANDLER - RAILED 20220302 130353
200 | CH | 3 | 200-CH-003 | Chute | SAG MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | CH | 4 | 200-CH-004 | Chute | SAG MILL REJECT CHUTE |  | Proton |  |  |  | 0
200 | CH | 5 | 200-CH-005 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | CH | 6 | 200-CH-006 | Chute | CONVEYOR TRANSFER CHUTE | Birikim | Birikim |  |  |  | 0
200 | HP | 1 | 200-BX-001 | Distribution launder | DISTRIBUTION LAUNDER |  | Proton |  |  |  | 0
200 | PB | 1 | 200-PB-001 | Pump Box | PRIMARY PUMP BOX |  | Proton |  |  |  | 0
200 | PP | 1 | 200-PP-001 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | PP | 2 | 200-PP-002 | PUMP | CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | VASA HD 455-100 NR/HC |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
200 | CY | 1 | 200-CY-001 | Hydrocyclone | BALL MILL CYCLONE 1 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CY | 2 | 200-CY-002 | Hydrocyclone | BALL MILL CYCLONE 2 | Weir Minerals | Weir Minerals |  |  |  | 0
200 | CH | 7 | 200-CH-007 | Chute | BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
200 | BM | 1 | 200-BM-001 | Ball Mill | BALL MILL | Metso Outotec | Chemitec/Metso Outotec | Select™ Ø3.40 m X 5.95 m EGL Ball Mill |  |  | 996.716 |  | X | X | Power: C.008312-EE-YRK-DWG-00040-02_900113293, MCC &PLC: 3067739 - RMG Beqtaqari - MO Select 3.4 m x 5.95 m EGL Ball Mill - Firm Proposal R4M | Includes the auxiliaries (7.2 kW of standby power included). 1 LW MCC & 1 PLC for Ball Mill is included in Vendor Scope. Medium Voltage switchgear panel is NOT included in Vendor Scope.
200 | TR | 2 | 200-TR-002 | Mill Trommel | BALL MILL TROMMEL | Metso Outotec | Metso Outotec |  |  |  | 0
200 | CH | 8 | 200-CH-008 | Chute | BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
200 | PT | 1 | 200-PT-001 | Scats Hopper | SCATS HOPPER |  | Proton |  |  |  | 0
200 | BN | 1 | 200-BN-001 | Ball pits | BALL PIT | RMG | Chemitec |  |  |  | 0
200 | MA | 1 | 200-MA-001 | Ball magnet | BALL MAGNET |  | Supplier |  |  |  | TBD |  |  |  | RMG to provide power
200 | BB | 1 | 200-BB-001 | Ball bucket | BALL BUCKET |  | Supplier |  |  |  | 0
200 | CH | 9 | 200-CH-009 | Chute | BALL CHARGER CHUTE |  | Supplier |  |  |  | 0
200 | CN | 1 | 200-CN-001 | Overhead crane | GRINDING AREA OVERHEAD CRANE |  | Chemitec |  | X | X | 60.4 |  |  |  |  | Preliminary power estimated by highest consumer offered
200 | BX | 4 | 200-BX-004 | Pebbles Box | PEBBLES BOX |  | Proton |  |  |  | 0 |  |  |  |  | Added 16.8.2022
200 | SP | 1 | 200-SP-001 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 2 | 200-SP-002 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
200 | SP | 3 | 200-SP-003 | SUMP PUMP | SUMP PUMP GRINDING AREA | Metso Outotec | Metso Outotec / Chemitec | VS100 L80 O3D85 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Pumps are in standby.
300 | SA | 1 | 300-SA-001/2 | Process Sampler | FLOTATION FEED (LSA SAMPLER (PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 1 | 300-SV-001/2 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-001/2 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 1 | 300-SA-001/1 | Metallurgical Sampler | FLOTATION FEED (MSA SAMPLER (EA)) | Metso Outotec | Chemitec |  |  |  | 15
300 | TK | 1 | 300-TK-001 | Tank | BULK ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
300 | AG | 1 | 300-AG-001 | AGITATOR | AGITATOR FOR BULK CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 15 |  |  |  | Offer SPX : 30966,30977
300 | FC | 1 | 300-FC-001 | Flotation Cell | BULK ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 2 | 300-FC-002 | Flotation Cell | BULK ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 3 | 300-FC-003 | Flotation Cell | BULK ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 4 | 300-FC-004 | Flotation Cell | BULK ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 5 | 300-FC-005 | Flotation Cell | BULK ROUGHER CELL 5 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 6 | 300-FC-006 | Flotation Cell | BULK SCAVENGER CELL 1 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | FC | 7 | 300-FC-007 | Flotation Cell | BULK SCAVENGER CELL 2 | Metso Outotec | Chemitec | TankCell® e30 |  |  | 45 |  |  |  | OU500752615
300 | CH | 3 | 300-CH-003 | Launder | CELLS 001-005 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | CH | 4 | 300-CH-004 | Launder | CELLS 006-007 DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 4 | 300-PB-004 | Pump Box | BULK ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 9 | 300-PP-009 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 10 | 300-PP-010 | PUMP | BULK ROUGHER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 22 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PB | 3 | 300-PB-003 | Pump Box | BULK SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 7 | 300-PP-007 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 8 | 300-PP-008 | PUMP | BULK SCAVENGER CONCENTRATE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 3 | 300-SA-003 | Process Sampler | BULK SCAVENGER CONCENTARET (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
300 | SV | 3 | 300-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | PB | 1 | 300-PB-001 | Pump Box | SCAVENGER TAILING PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 3 | 300-PP-003 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 4 | 300-PP-004 | PUMP | SCAVENGER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 18.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 2 | 300-SA-002 | Metallurgical Sampler | BULK SCAVENGER TAILINGS (MSA SAMPLER (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
300 | CY | 1 | 300-CY-001 | Hydrocyclone | REGRIND CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | CY | 2 | 300-CY-002 | Hydrocyclone | REGRIND CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 Way 400CVX10 Radial |  |  | 0
300 | BX | 1 | 300-BX-001 | Distribution Box | DISTRIBUTION BOX 1 |  | Proton |  |  |  | 0
300 | CH | 1 | 300-CH-001 | Chute | REGRIND BALL MILL FEED CHUTE |  | Proton |  |  |  | 0
300 | BM | 1 | 300-BM-001 | Ball Mill | REGRIND BALL MILL | CEMTEC | Chemitec/CEMTEC | Wet Ball Mill Ø2.40 m X 3.75 m |  |  | 254.61 |  |  | X | 208206-740-100-MBM-ELA001-00, Appendix 1_A113245-05_commercial_offer_ball_mill | Power includes auxiliaries
300 | TR | 1 | 300-TR-001 | Mill Trommel | REGRIND BALL MILL TROMMEL | CEMTEC | CEMTEC |  |  |  | 0
300 | CH | 1 | 300-CH-002 | Chute | REGRIND BALL MILL DISCHARGE CHUTE |  | Proton |  |  |  | 0
300 | PB | 2 | 300-PB-002 | Pump Box | REGRIND CYCLONE FEED PUMP BOX |  | Chemitec |  |  |  | 0
300 | PP | 5 | 300-PP-005 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | PP | 6 | 300-PP-006 | PUMP | REGRIND CYCLONE FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4HC |  | X | 37 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
300 | SA | 5 | 300-SA-005 | Process Sampler | Pb ROUGHER FEED-GOING TO Zn COND.(LSA SAMPLER (EA&PSD)) |  | Chemitec |  |  |  | 0
300 | SV | 5 | 300-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | SA | 4 | 300-SA-004 | Process Sampler | Pb ROUGHER FEED-LSA SAMPLER (EA&PSD) |  | Chemitec |  |  |  | 0
300 | SV | 4 | 300-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
300 | CN | 1 | 300-CN-001 | Overhead Crane | BULK FLOTATION AND REGRINDING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
300 | SP | 1 | 300-SP-001 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 2 | 300-SP-002 | SUMP PUMP | SUMP PUMP FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | SP | 3 | 300-SP-003 | SUMP PUMP | SUMP PUMP REGRINDING BALL MILL | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
300 | ES | 1 | 300-ES-001 | Emergency Station | EMERGENCY SHOWER & EYE WASH STATION |  | Proton |  |  |  | 0
305 | TK | 1 | 305-TK-001 | TANK | TAILINGS THICKENER FEED TANK |  | Chemitec/Proton | 4 m3 |  |  | 0
305 | RA | 1 | 305-RA-001 | RAKE MECHANISM | TAILINGS THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 4 |  |  |  | 3274949 Technical Description rev.06
305 | TH | 1 | 305-TH-001 | THICKENER | TAILINGS THICKENER | Metso Outotec | Chemitec | HRT - 16 m | X |  | 1.5 |  |  |  | OU500759567_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
305 | PP | 1 | 305-PP-001 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 2 | 305-PP-002 | PUMP | TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | TK | 2 | 305-TK-002 | TANK | TAILINGS FILTER FEED SURGE TANK |  | Chemitec/Proton | 250 m3 |  |  | 0
305 | AG | 2 | 305-AG-002 | AGITATOR | AGITATOR FOR TAILINGS FILTER FEED SURGE TANK |  | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
305 | PP | 5 | 305-PP-005 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 6 | 305-PP-006 | PUMP | TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 110 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | FL | 1 | 305-FL-001 | FILTER PRESS | TAILINGS FILTER | Diemme | Chemitec/Diemme | ME 2000 F15 |  |  | 49.62 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Bulk Tailings Filter Press is included in Vendor Scope.
305 | PB | 2 | 305-PB-002 | PUMP BOX | TAILINGS THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | PP | 8 | 305-PP-008 | PUMP | TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
305 | CH | 1 | 305-CH-001 | CHUTE | TAILINGS PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
305 | CV | 1 | 305-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-1000 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 2 | 305-CV-002 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | XE400 2+2 |  |  | 15 |  |  |  | Birikim Offer # 211600 R2
305 | CV | 3 | 305-CV-003 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125, 2+2 |  |  | 11 |  |  |  | Birikim Offer # 211600 R2
305 | BN | 1 | 305-BN-001 | TAILINGS SILO | TAILINGS SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
305 | CN | 1 | 305-CN-001 | OVERHEAD CRANE | TAILINGS DEWATERING OVERHAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
305 | SP | 1 | 305-SP-001 | SUMP PUMP | SUMP PUMP FOR TAILINGS THICKENER AREA | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 30 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 2 | 305-SP-002 | SUMP PUMP | SUMP PUMP FOR TAILINGS FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | SP | 3 | 305-SP-003 | SUMP PUMP | FILTER WASHING AND RINSING WASHING SUMP PUMP | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
305 | TK | 4 | 305-TK-004 | TANK | FILTER WASHING WATER TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
305 | PP | 7 | 305-PP-007 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 200 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | P&ID shows 137 kW. (MH: 137 might me working power)
305 | PP | 8 | 305-PP-008 | PUMP | HIGH PRESSURE WASHING PUMP | Diemme | Diemme | Piston type pump |  | X | 37 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
310 | TK | 1 | 310-TK-001 | Tank | Pb ROUGHER CONDITIONING TANK |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-001 | AGITATOR | AGITATOR FOR Pb CONDITIONING TANK | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | FC | 1 | 310-FC-001 | Flotation Cell | Pb ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 2 | 310-FC-002 | Flotation Cell | Pb ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 3 | 310-FC-003 | Flotation Cell | Pb ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 4 | 310-FC-004 | Flotation Cell | Pb ROUGHER CELL 4 | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | FC | 5 | 310-FC-005 | Flotation Cell | Pb SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e5 |  |  | 11 |  |  |  | OU500752615
310 | PB | 1 | 310-PB-001 | Pump Box | DEWATERING CYCLONES FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 1 | 310-PP-001 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 2 | 310-PP-002 | PUMP | DEWATERING CYCLONES FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 11 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 8 | 310-PB-008 | Pump Box | Pb SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 17 | 310-PP-017 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 18 | 310-PP-018 | PUMP | Pb SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | CY | 1 | 310-CY-001 | Hydrocyclone | DEWATERING CYCLONE 1 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | CY | 2 | 310-CY-002 | Hydrocyclone | DEWATERING CYCLONE 2 | Weir Minerals | Weir Minerals | Cavex 4 way 100CVX Radial |  |  | 0
310 | HP | 1 | 310-HP-001 | Grinding Media Addition System | MEDIA ADDITION SYSTEM | Metso Outotec | Metso Outotec |  |  |  | 0
310 | BN | 1 | 310-BN-001 | Bin | MEDIA HANDLING BIN | Metso Outotec | Metso Outotec |  |  |  | 0
310 | HP | 1 | 310-HP-001 | Hopper | MEDIA HOPPER | Metso Outotec | Metso Outotec |  |  |  | 0
310 | SD | 1 | 310-SD-001 | Mill | FINE GRIND MILL | Metso Outotec | Metso Outotec | SMD-E-90 |  |  | 92.41 |  |  |  | C.008574-EE-YRK-DWG-00030 | Including auxiliary equipment
310 | PB | 2 | 310-PB-002 | Pump Box | Pb 1st CLEANER FEED PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 3 | 310-PP-003 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 4 | 310-PP-004 | PUMP | Pb 1st CLEANER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 2 | 310-SA-002 | Process Sampler | Pb ROUGHER CONCENTRATE (ASA SAMPLER (EA & PSD)) |  | Chemitec |  |  |  | 0
310 | SV | 6 | 310-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 300-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SV | 2 | 310-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | TK | 2 | 310-TK-002 | Tank | Pb 1st CLEANER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 1 | 310-AG-002 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 1 | SPX Flow | SPX Flow |  | X |  | 5.5 |  |  |  | Offer SPX : 30966,30977
310 | TK | 3 | 310-TK-003 | Tank | Pb 1st CLEANER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
310 | AG | 3 | 310-AG-003 | AGITATOR | AGITATOR FOR 1st CLEANER COND. TANK 2 | SPX Flow | Supplier |  | X |  | 3 |  |  |  | Offer SPX : 30966,30977
310 | FC | 6 | 310-FC-006 | Flotation Cell | Pb 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 7 | 310-FC-007 | Flotation Cell | Pb 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 8 | 310-FC-008 | Flotation Cell | Pb 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | SA | 4 | 310-SA-004 | Process Sampler | Pb 1st CLEANER TAILING (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 4 | 310-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 3 | 310-PB-003 | Pump Box | Pb 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 5 | 310-PP-005 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 6 | 310-PP-006 | PUMP | Pb 3rd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 9 | 310-FC-009 | Flotation Cell | Pb 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | FC | 10 | 310-FC-010 | Flotation Cell | Pb 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
310 | PB | 4 | 310-PB-004 | Pump Box | Pb 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 7 | 310-PP-007 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 8 | 310-PP-008 | PUMP | Pb 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PB | 9 | 310-PB-009 | Pump Box | Pb 2nd CLEANER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 19 | 310-PP-019 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 20 | 310-PP-020 | PUMP | Pb 2nd CLEANER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 | X | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 5 | 310-SA-005 | Process Sampler | Pb 2nd CLEANER CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 5 | 310-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | FC | 11 | 310-FC-011 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 12 | 310-FC-012 | Flotation Cell | Pb 3rd CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 13 | 310-FC-013 | Flotation Cell | Pb 3rd CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | SA | 6 | 310-SA-006 | Process Sampler | Pb 3rd CLEANER TAILINGS (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | PB | 5 | 310-PB-005 | Pump Box | Pb 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 9 | 310-PP-009 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 10 | 310-PP-010 | PUMP | Pb 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | FC | 14 | 310-FC-014 | Flotation Cell | Pb 4th CLEANER CELLS | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 15 | 310-FC-015 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | FC | 16 | 310-FC-016 | Flotation Cell | Pb 4th CLEANER CELL | Metso Outotec | Chemitec | RCS 0,8 |  |  | 5.5 |  |  |  | OU500767867_R0
310 | PB | 6 | 310-PB-006 | Pump Box | Pb 4th CLEANER CONC. PUMP BOX |  | Chemitec |  |  | X | 0
310 | PP | 11 | 310-PP-011 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 12 | 310-PP-012 | PUMP | Pb 4th CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 1 | 310-SA-001 | Metallurgical Sampler | Pb FINAL CONCENTRATE (RD-ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 1 | 310-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | PB | 10 | 310-PB-010 | Pump Box | Pb TAILINGS DISCHARGE PUMP BOX |  | Chemitec |  |  |  | 0
310 | PP | 13 | 310-PP-013 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | PP | 14 | 310-PP-014 | PUMP | Pb TAILINGS DISCHARGE PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
310 | SA | 3 | 310-SA-003 | Process Sampler | Pb TAILINGS (PSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
310 | SV | 3 | 310-SV-003 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 310-SA-003 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
310 | SP | 1 | 310-SP-001 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 2 | 310-SP-002 | SUMP PUMP | SUMP PUMP Pb FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | SP | 3 | 310-SP-003 | SUMP PUMP | SUMP PUMP FINE GRINDING MILL | Metso Outotec | Metso Outotec / Chemitec | VS25 L80 O5D85 HC | X | X | 2.2 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
310 | CH | 1 | 310-CH-001 | Launder | Pb Rougher Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 2 | 310-CH-002 | Launder | Pb Rougher Scav Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 3 | 310-CH-003 | Launder | Pb 1st cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 4 | 310-CH-004 | Launder | Pb 2nd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 5 | 310-CH-005 | Launder | Pb 3rd cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
310 | CH | 6 | 310-CH-006 | Launder | Pb 4th cl Launder |  | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | TK | 1 | 320-TK-001 | Tank | Zn ROUGHER CONDITIONING TANK 1 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 1 | 320-AG-001 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 1 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | TK | 2 | 320-TK-002 | Tank | Zn ROUGHER CONDITIONING TANK 2 |  | Chemitec/Proton |  |  |  | 0
320 | AG | 2 | 320-AG-002 | AGITATOR | AGITATOR FOR Zn CONDITIONING TANK 2 | SPX Flow | SPX Flow |  | X |  | 11 |  |  |  | Offer SPX : 30966,30977
320 | FC | 1 | 320-FC-001 | Flotation Cell | Zn ROUGHER CELL 1 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 2 | 320-FC-002 | Flotation Cell | Zn ROUGHER CELL 2 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 3 | 320-FC-003 | Flotation Cell | Zn ROUGHER CELL 3 | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | FC | 4 | 320-FC-004 | Flotation Cell | Zn SCAVENGER CELL | Metso Outotec | Chemitec | TankCell® e10 |  |  | 22 |  |  |  | OU500752615
320 | PB | 1 | 320-PB-001 | Pump Box | Zn ROUGHER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 1 | 320-PP-001 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 2 | 320-PP-002 | PUMP | Zn ROUGHER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 1 | 320-SA-001 | Process Sampler | Zn ROUGHER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 1 | 320-SV-001 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-001 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SA | 7 | 320-SA-007 | Process Sampler | Zn ROUGHER SCAVENGER TAILINGS (LSA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 7 | 320-SV-007 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-007 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 7 | 320-PB-007 | Pump Box | Zn SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 13 | 320-PP-013 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 14 | 320-PP-014 | PUMP | Zn SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 2 | 320-PB-002 | Pump Box | Zn ROUGHER TAILINGS PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 3 | 320-PP-003 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 4 | 320-PP-004 | PUMP | Zn ROUGHER TAILINGS PUMP | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 | X | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 3 | 320-SA-003 | Metallurgical Sampler | Zn TAILINGS (MSA Sampler (EA)) | Metso Outotec | Metso Outotec |  |  |  | 15 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
320 | FC | 5 | 320-FC-005 | Flotation Cell | Zn 1st CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 6 | 320-FC-006 | Flotation Cell | Zn 1st CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 7 | 320-FC-007 | Flotation Cell | Zn 1st CLEANER CELL 3 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 8 | 320-FC-008 | Flotation Cell | Zn 1st CLEANER SCAVENGER CELL | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 2 | 320-SA-002 | Process Sampler | Zn 1st CLEANER-SCAVENGER TAILINGS (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 2 | 320-SV-002 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-002 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 6 | 320-PB-006 | Pump Box | Zn 1st CLEANER SCAVENGER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 11 | 320-PP-011 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 12 | 320-PP-012 | PUMP | Zn 1st CLEANER SCAVENGER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR50 FNR-S O4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PB | 3 | 320-PB-003 | Pump Box | Zn 1st CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 5 | 320-PP-005 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 6 | 320-PP-006 | PUMP | Zn 1st CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 5 | 320-SA-005 | Process Sampler | Zn 1st CLEANER CONCENTRATE (ASA SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 5 | 320-SV-005 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-005 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | FC | 9 | 320-FC-009 | Flotation Cell | Zn 2nd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 10 | 320-FC-010 | Flotation Cell | Zn 2nd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | SA | 6 | 320-SA-006 | Process Sampler | Zn 2nd CLANER TAILINGS (ADAPTED RD SAMPLER (EA)) |  | Chemitec |  |  |  | 0
320 | SV | 6 | 320-SV-006 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-006 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | PB | 4 | 320-PB-004 | Pump Box | Zn 2nd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 7 | 320-PP-007 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5. |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 8 | 320-PP-008 | PUMP | Zn 2nd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 5.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | FC | 11 | 320-FC-011 | Flotation Cell | Zn 3rd CLEANER CELL 1 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | FC | 12 | 320-FC-012 | Flotation Cell | Zn 3rd CLEANER CELL 2 | Metso Outotec | Chemitec | RCS 3 |  |  | 11 |  |  |  | OU500767867_R0
320 | PB | 5 | 320-PB-005 | Pump Box | Zn 3rd CLEANER CONC. PUMP BOX |  | Chemitec |  |  |  | 0
320 | PP | 9 | 320-PP-009 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 10 | 320-PP-010 | PUMP | Zn 3rd CLEANER CONC. PUMP | Metso Outotec | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 2.2 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 15 | 320-PP-015 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | PP | 16 | 320-PP-016 | PUMP | Bulk Cleaner Tailings Pump | Metso Outotec | Metso Outotec / Chemitec | HR150 FNR-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
320 | SA | 4 | 320-SA-004 | Metallurgical Sampler | Zn FINAL CONCENTRATE- RD SAMPLER (EA) |  | Chemitec |  |  |  | 0
320 | SV | 4 | 320-SV-004 | Sampler Valve Arrangement | VALVE ARRANGMENT FOR SAMPLER 320-SA-004 | Metso Outotec | Metso Outotec |  |  |  | 0 |  |  |  |  | Added 9.8.2022
320 | SP | 1 | 320-SP-001 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | SP | 2 | 320-SP-002 | SUMP PUMP | SUMP PUMP Zn FLOTATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
320 | CH | 1 | 320-CH-001 | Launder | Zn Rougher Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 2 | 320-CH-002 | Launder | Zn Rougher Scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 3 | 320-CH-003 | Launder | Zn 1st cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 4 | 320-CH-004 | Launder | Zn 1st cl scav Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 5 | 320-CH-005 | Launder | Zn 2nd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
320 | CH | 6 | 320-CH-006 | Launder | Zn 3rd cl Launder | Supplier | Supplier |  |  |  | 0 |  |  |  |  | Added 19.07.2022
325 | TK | 1 | 325-TK-001 | TANK | Zn TAILINGS THICKENER FEED TANK |  | Chemitec/Proton | 12 m3 |  |  | 0
325 | PP | 1 | 325-PP-001 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 2 | 325-PP-002 | PUMP | Zn TAILINGS THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | HR100 FNR-S C4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | TK | 2 | 325-TK-002 | TANK | Zn TAILINGS FILTER FEED SURGE TANK |  | Chemitec/Proton | 250 m3 |  |  | 0
325 | AG | 2 | 325-AG-002 | AGITATOR | AGITATOR FOR Zn TAILINGS FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 55 |  |  |  | Offer SPX : 30966,30977
325 | PP | 5 | 325-PP-005 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 6 | 325-PP-006 | PUMP | Zn TAILINGS PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM200 FHC-S C5 |  | X | 90 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PB | 2 | 325-PB-002 | PUMP BOX | Zn TAILINGS FILTRATE PUMP BOX |  | Chemitec | 30 m3 |  |  | 0
325 | PP | 7 | 325-PP-007 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | PP | 8 | 325-PP-008 | PUMP | Zn TAILINGS FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM100 FHC-S C4 |  | X | 7.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
325 | CH | 1 | 325-CH-001 | CHUTE | Zn TAILINGS PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
325 | SP | 1 | 325-SP-001 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS THICKENER AREA | Metso Outotec | Metso Outotec / Chemitec | VSHM100 L120 C5 HC | X | X | 7.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Will be updated with MOs next rpoposal
325 | SP | 2 | 325-SP-002 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS FILTER FEED TANK AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
325 | SP | 3 | 325-SP-003 | SUMP PUMP | SUMP PUMP FOR Zn TAILINGS FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 1.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
400 | TK | 1 | 400-TK-001 | TANK | Pb CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 1 | 400-RA-001 | RAKE MECHANISM | Pb CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 1 | 400-TH-001 | THICKENER | Pb CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759542_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 1 | 400-PP-001 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 2 | 400-PP-002 | PUMP | Pb CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 40 | X | X | 1.5 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PB | 1 | 400-PB-001 | PUMP BOX | Pb CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 3 | 400-PP-003 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 4 | 400-PP-004 | PUMP | Pb CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM50 FHC-S W8WFR |  | X | 1.5 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 2 | 400-TK-002 | TANK | Pb CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 2 | 400-AG-002 | AGITATOR | AGITATOR FOR Pb CONCENTRATE FEED SURGE TANK |  | SPX Flow | SPX Flow | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 5 | 400-PP-005 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 6 | 400-PP-006 | PUMP | Pb CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 1 | 400-FL-001 | FILTER PRESS | Pb CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.1500 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Pb Concentrate Filter Press is included in Vendor Scope.
400 | PB | 1 | 400-PB-003 | PUMP BOX | Pb CONCENTRATE FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 7 | 400-PP-007 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 8 | 400-PP-008 | PUMP | Pb CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 1 | 400-CH-001 | CHUTE | Pb CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 1 | 400-CV-001 | BELT CONVEYOR | CONVEYOR | Birikim | Birikim | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 1 | 400-SA-001 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 2 | 400-CV-002 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 1 | 400-BN-001 | TAILINGS SILO | Pb CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 1 | 400-FE-001 | SCREW EXTRACTOR | Pb CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 1 | 400-BS-001 | BAGGING SYSTEM | Pb CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | SP | 1 | 400-SP-001 | SUMP PUMP | SUMP PUMP FOR Pb CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC |  | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Tag changed. 3.8.2022
400 | PP | 18 | 400-PP-018 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 9.2 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER | NOTE CHANGED TAG
400 | TK | 3 | 400-TK-003 | TANK | Zn CONCENTRATE THICKENER FEED TANK |  | Chemitec/Proton | 1 m3 |  |  | 0
400 | RA | 2 | 400-RA-002 | RAKE MECHANISM | Zn CONCENTRATE THICKENER RAKE MECHANISM | Metso Outotec | Metso Outotec |  | X |  | 1.1 |  |  |  | 3274949 Technical Description rev.06
400 | TH | 2 | 400-TH-002 | THICKENER | Zn CONCENTRATE THICKENER | Metso Outotec | Chemitec | HRT - 4m | X |  | 2.1 |  |  |  | OU500759554_R0_LIST OF ELECTRICAL CONSUMERS | Energy consumers are the control panel and the oil heater
400 | PP | 9 | 400-PP-009 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PP | 10 | 400-PP-010 | PUMP | Zn CONCENTRATE THICKENER UNDERFLOW PUMP | Metso Outotec | Metso Outotec / Chemitec | Bredel 50 | X | X | 3 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001 | Will be updated with MOs next rpoposal
400 | PB | 2 | 400-PB-002 | PUMP BOX | Zn CONCENTRATE THICKENER OVERFLOW PUMP BOX |  | Chemitec | 1 m3 |  |  | 0
400 | PP | 11 | 400-PP-011 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 |  |  |  | Quotation_Concentrator Pumps_WEIR
400 | PP | 12 | 400-PP-012 | PUMP | Zn CONCENTRATE THICKENER OVERFLOW PUMP | Weir Minerals | Weir Minerals / Chemitec | HM75 FHC-S W8WFR |  | X | 2.2 | X |  |  | Quotation_Concentrator Pumps_WEIR
400 | TK | 4 | 400-TK-004 | TANK | Zn CONCENTRATE FILTER FEED SURGE TANK |  | Chemitec/Proton | 20 m3 |  |  | 0
400 | AG | 4 | 400-AG-004 | AGITATOR | AGITATOR FOR Zn CONCENTRATE FEEDER SURGE TANK | SPX Flow | SPX Flow |  | X | X | 11 |  |  |  | Offer SPX : 30966,30977
400 | PP | 13 | 400-PP-013 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 14 | 400-PP-014 | PUMP | Zn CONCENTRATE PRESSURE FILTER FEED PUMP | Metso Outotec | Metso Outotec / Chemitec | HM75 FHC-S C4 |  | X | 15 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | FL | 2 | 400-FL-002 | FILTER PRESS | Zn CONCENTRATE FILTER | Diemme | Chemitec/Diemme | ME1000.2700 |  |  | 7.5 |  |  | X | Appendix 1_X-210114_4_RMG_2ME.2000F_2ME1000 - FINAL OFFER | 1 PLC for Zn Concentrate Filter Press is included in Vendor Scope.
400 | PB | 4 | 400-PB-004 | PUMP BOX | Zn CONCENTRATE THICKENER FILTRATE PUMP BOX |  | Chemitec |  |  |  | 0 |  |  |  |  | Is a tank in the PFD, should make it a pump box
400 | PP | 15 | 400-PP-015 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 |  |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | PP | 16 | 400-PP-016 | PUMP | Zn CONCENTRATE FILTRATE RELEASE PUMP | Metso Outotec | Metso Outotec / Chemitec | HM50 FHC-S O4 |  | X | 4 | X |  |  | MO - Slurry Pumps Proposal PT05082022-1 - P1384-300-PC-001
400 | CH | 2 | 400-CH-002 | CHUTE | Zn CONCENTRATE PRESSURE FILTER DISCHARGE CHUTE | Supplier | Supplier |  |  |  | 0
400 | CV | 3 | 400-CV-003 | BELT CONVEYOR | CONVEYOR | Supplier | Supplier | St-630 |  |  | 5.5 |  |  |  | Birikim Offer # 211600 R2
400 | SA | 2 | 400-SA-002 | DRY SAMPLER | DRY SAMPLER | Siebtechnik | Siebtechnik | Down Pipe Swivel Sampler |  |  | 0.37 |  |  |  | Sebtechnik offer: SKM_C30822081015350
400 | CV | 4 | 400-CV-004 | BUCKET CONVEYOR | BUCKET CONVEYOR | Birikim | Birikim | 5EP 125 2+2 |  |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | BN | 2 | 400-BN-002 | TAILINGS SILO | Zn CONCENTRATE SILO | Birikim | Birikim |  | X |  | 1.95 |  |  |  | Birikim Offer # 211600 R2
400 | FE | 2 | 400-FE-002 | SCREW EXTRACTOR | Zn CONCENTRATE SCREW EXTRACTOR | Birikim | Birikim |  | X |  | 4 |  |  |  | Birikim Offer # 211600 R2
400 | BS | 2 | 400-BS-002 | BAGGING SYSTEM | Zn CONCENTRATE BAGGING SYSTEM | Birikim | Birikim |  | X |  | 2.2 |  |  |  | Birikim Offer # 211600 R2
400 | CN | 1 | 400-CN-001 | OVERHEAD CRANE | CONCENTRATE DEWATERING OVERHEAD CRANE |  | Chemitec |  | X | X | 36.2 |  |  |  | Provided by RMG
400 | PP | 17 | 400-PP-017 | PUMP | RINSE WASHING PUMP | Diemme | Diemme | Centrifugal pump |  | X | 11 |  |  |  | X-210114_2_CHEMITEC_2ME.2000F_2ME1000 - COMMERCIAL OFFER
400 | SP | 2 | 400-SP-002 | SUMP PUMP | SUMP PUMP FOR Zn CONCENTRATE FILTRATION AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O4D75 HC | X | X | 3 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001 | Added 4.8.2022.
500 | XX | 1 | 500-XX-001 | REAGENT MIXING AND DOSING | MIBC MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.4 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 2 | 500-XX-002 | REAGENT MIXING AND DOSING | AERO 208 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.45 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 3 | 500-XX-003 | REAGENT MIXING AND DOSING | W31 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 0.18 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 4 | 500-XX-004 | REAGENT MIXING AND DOSING | SODA ASH MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 10.65 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 5 | 500-XX-005 | REAGENT MIXING AND DOSING | Ca(OH)2 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 8.25 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 6 | 500-XX-006 | REAGENT MIXING AND DOSING | DEP347 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 1.12 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 7 | 500-XX-007 | REAGENT MIXING AND DOSING | ZnSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.23 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 8 | 500-XX-008 | REAGENT MIXING AND DOSING | CuSO4 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 9 | 500-XX-009 | REAGENT MIXING AND DOSING | NaCN MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11.6 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 10 | 500-XX-010 | REAGENT MIXING AND DOSING | SIPX MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 11 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 11 | 500-XX-011 | REAGENT MIXING AND DOSING | Magnafloc 1687 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.62 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 12 | 500-XX-012 | REAGENT MIXING AND DOSING | Magnafloc 10 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  | X |  | 3.34 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | XX | 13 | 500-XX-013 | REAGENT MIXING AND DOSING | Magnafloc 333 MIXING AND DOSING PACKAGE UNIT |  | Turun Asennnus/Chemitec |  |  |  | 2.22 |  |  | X | Updated to Turun | Package delivery - Detailed internal components list in vendor engineering package
500 | SP | 1 | 500-SP-001 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 2 | 500-SP-002 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 1 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 3 | 500-SP-003 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 2 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 4 | 500-SP-004 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 3 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
500 | SP | 5 | 500-SP-005 | SUMP PUMP | PORTABLE SUMP PUMP FOR REAGENT AREA 4 |  | Turun Asennnus/Chemitec | Portable sump pump | X |  | 4 |  |  |  | Turun mail communication
600 | CP | 1 | 600-CP-001 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 2 | 600-CP-002 | AIR COMPRESSOR | PLANT AIR COMPRESSOR | Atlas Copco | Atlas Copco/Chemitec | GA 315 |  |  | 360 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 3 | 600-CP-003 | AIR COMPRESSOR | PLANT AIR COMPRESSOR - STAND BY | Atlas Copco | Atlas Copco/Chemitec | GA 315 | X |  | 360 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | AR | 1 | 600-AR-001 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AR | 2 | 600-AR-002 | AIR RECEIVER | PLANT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 40 m3 |  |  | 0
600 | AD | 1 | 600-AD-001 | AIR DRYER | INSTRUMENT AIR DRYER | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0
600 | AD | 2 | 600-AD-002 | AIR DRYER | INSTRUMENT AIR DRYER-STAND BY | Atlas Copco | Atlas Copco/Chemitec |  |  |  | 0 | X
600 | AR | 5 | 600-AR-005 | AIR RECEIVER | INSTRUMENT AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 10 m3 |  |  | 0
600 | BL | 1 | 600-BL-001 | AIR BLOWER | FLOTATION AIR BLOWER |  | Continental/Chemitec |  |  |  | 160 |  |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | BL | 2 | 600-BL-002 | AIR BLOWER | FLOTATION AIR BLOWER - STAND BY |  | Continental/Chemitec |  |  |  | 160 | X |  |  | Continental offer: QUOTATION_EN_No_CI-INT.11.22054
600 | FL | 1 | 600-IF-001 | INLET FILTER | INLET FILTER FOR AIR BLOWER |  | Continental/Chemitec |  |  |  | 0
600 | FL | 2 | 600-IF-002 | INLET FILTER | INLET FILTER FOR AIR BLOWER-STAND BY |  | Continental/Chemitec |  |  |  | 0 | X
600 | CP | 4 | 600-CP-004 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-2
600 | CP | 5 | 600-CP-005 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-3
600 | CP | 6 | 600-CP-006 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-4
600 | CP | 7 | 600-CP-007 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 |  |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-5
600 | CP | 8 | 600-CP-008 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-6
600 | CP | 9 | 600-CP-009 | AIR COMPRESSOR | FILTER PRESS AIR COMPESSOR-STAND BY | Atlas Copco | Atlas Copco/Chemitec | LT20 |  |  | 15 | X |  |  | 3511550 - AIF_Chemitec_GA_Georgia_20220822142814151-7
600 | AR | 3 | 600-AR-003 | AIR RECEIVER | FILTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | AR | 4 | 600-AR-004 | AIR RECEIVER | FLTER PRESS AIR RECEIVER | Atlas Copco | Atlas Copco/Chemitec | 4 m3 |  |  | 0
600 | TK | 1 | 600-TK-001 | WATER TANK | PROCESS WATER TANK BULK FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 1 | 600-PP-001 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 2 | 600-PP-002 | PUMP | Bulk Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/150D-MU | X | X | 45 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 2 | 600-TK-002 | WATER TANK | PROCESS WATER TANK Pb FLOTATION |  |  | 30 m3 |  |  | 0
600 | PP | 3 | 600-PP-003 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 4 | 600-PP-004 | PUMP | Pb Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 100/80B-MU | X | X | 3 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 3 | 600-TK-003 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | TK | 4 | 600-TK-004 | WATER TANK | PROCESS WATER TANK Zn FLOTATION |  |  | 100 m3 |  |  | 0
600 | PP | 5 | 600-PP-005 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 6 | 600-PP-006 | PUMP | Zn Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | 200/200D-MU | X | X | 55 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 5 | 600-TK-005 | WATER TANK | PROCESS WATER TANK BLEEDING TANK |  |  | 20 m3 |  |  | 0
600 | PP | 7 | 600-PP-007 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 8 | 600-PP-008 | PUMP | Bleeding Process Water Pumps | Weir Minerals | Weir Minerals / Chemitec | TBD | X | X | 11 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 6 | 600-TK-006 | WATER TANK | FRESH WATER TANK |  |  | 300 m3 |  |  | 0
600 | PP | 9 | 600-PP-009 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 10 | 600-PP-010 | PUMP | FRESH WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | MRD 150-175 | X | X | 110 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 11 | 600-PP-011 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 |  |  |  | Quotation_Concentrator Pumps_WEIR
600 | PP | 12 | 600-PP-012 | PUMP | GLAND SEAL WATER PUMP | Weir Minerals | Weir Minerals / Chemitec | VE50 | X | X | 15 | X |  |  | Quotation_Concentrator Pumps_WEIR
600 | TK | 7 | 600-TK-007 | WATER TANK | FIRE WATER TANK |  |  | 150 m3 |  |  | 0 |  |  |  | 1. Fire extinguishing system - 380V, 50Hz, 37kW, 97.3 A;
600 | PP | 13 | 600-PP-013 | PUMP | FIRE WATER PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 2. Alarm system - 220V, 500 Watt, 2,3 A; | Information given by RMG on 5.9.2022
600 | PP | 14 | 600-PP-014 | PUMP | FIRE WATER JOCKEY PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 3. Emergency lighting - 220V, 22.4 kW, 100.1 A;
600 | PP | 15 | 600-PP-015 | PUMP | FIRE WATER DIESEL PUMP |  |  | Not in Scope | X | X | TBD |  |  |  | 4. Emergency alarm/sirens - 220V, 500 Watt, 2.3A.
600 | SP | 1 | 600-SP-001 | SUMP PUMP | SUMP PUMP Zn-Pb PROCESS WATER TANKS | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 4 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
600 | SP | 2 | 600-SP-002 | SUMP PUMP | SUMP PUMP Zn-Pb TAILINGS, BULK & FRESH WATER TANKS AREA | Metso Outotec | Metso Outotec / Chemitec | VS50 L80 O5 HC | X | X | 5.5 |  |  |  | MO - Sump Pumps Proposal PT05082022-2 - P1384-600-PC-001
700 | PA | 1 | 700-PA-001 | PARTICLE SIZE ANALYSER | PARTICLE SIZE ANALYSER | Metso Outotec | Chemitec |  |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 4 | 700-MP-004 | MULTIPLEXER | PARTICLE SIZE ANALYSER MULTIPLEXER | Metso Outotec | Chemitec |  |  |  | 0
700 | TK | 1 | 700-TK-001 | TANK | DILUTION WATER TANK | Metso Outotec | Chemitec |  |  |  | 0
700 | EA | 1 | 700-EA-001 | ELEMENTAL ANALYSER | ELEMENTAL ANALYSER | Metso Outotec | Chemitec |  |  |  | 1.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 1 | 700-PP-001 | PUMP | SAMPLE TRANSFER PUMP MXA 1 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 2 | 700-PP-002 | PUMP | SAMPLE TRANSFER PUMP MXA 2 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 4 | 700-PP-004 | PUMP | SAMPLE TRANSFER PUMP PSA - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | MP | 1 | 700-MP-001 | MULTIPLEXER | EA MULTIPLEXER 1 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 2 | 700-MP-002 | MULTIPLEXER | EA MULTIPLEXER 2 | Metso Outotec | Chemitec |  |  |  | 0
700 | MP | 3 | 700-MP-003 | MULTIPLEXER | EA MULTIPLEXER 3 | Metso Outotec | Chemitec |  |  |  | 0
700 | PV | 1 | 700-VP-001 | VERTICAL PUMP | SAMPLE RETURN PUMP 1 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 2 | 700-VP-002 | VERTICAL PUMP | SAMPLE RETURN PUMP 2 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 3 | 700-VP-003 | VERTICAL PUMP | SAMPLE RETURN PUMP 3 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 4 | 700-VP-004 | VERTICAL PUMP | SAMPLE RETURN PUMP 4 | Metso Outotec |  | VF80 |  |  | 5.5 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PB | 1 | 700-PB-001 | PUMP BOX | Pb Final Conc. Pump box | [5 empty] | 0
700 | PP | 5 | 700-PP-005 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 |  |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 6 | 700-PP-006 | PUMP | Pb Final Conc. Pump | Weir Minerals | Metso Outotec / Chemitec | HR75 FNR-S C4 |  | X | 4 | X |  |  | Quotation_Concentrator Pumps_WEIR
700 | PP | 8 | 700-PP-008 | PUMP | DILUTION WATER PUMP | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PP | 3 | 700-PP-003 | PUMP | SAMPLE TRANSFER PUMP MXA 3 - EA | Metso Outotec |  | TBD |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | PV | 7 | 700-PP-007 | PUMP | SAMPLE TRANSFER VERTICAL PUMP | Metso Outotec |  | VF50 |  |  | 1 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
700 | DP | 1 | 700-DP-001 | DEMULTIPLEXER | DEMULTIPLEXER | Metso Outotec |  |  |  |  | 0 |  |  |  | MO - 313797_RMG_automation for Beqtaqari_R6_MO_Automation_firm_proposal
999 |  |  |  | Lighting - Main building |  |  |  |  | X |  | 20 |  |  |  | RMG Email from 6.9.2022 | 1. Reserve cells/sections in MCCs – We would prefer to reserve 1 free cell in MCCs for each location (crusher and main building MCCs) with 50kW in order to have spare capacity for connecting additional HVAC, water mist sprayers at ore pad, other equipment.
999 |  |  |  | HVAC - Crusher building |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Stockpile |  |  |  |  | X |  | 50
999 |  |  |  | HVAC - Main building |  |  |  |  | X |  | 70
999 |  |  |  | AC for transfromer and MCC room |  |  |  |  | X |  | 50
Note on J137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should not be necessary to use, but could be good to have the option.
Note on J219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can send it to the Zn RF or the Bulk RF as long as the valves in the split are energized.
Note on J296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: COuld be just emptied, but would be nice to be able to keep it agitated.
Note on J360: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Energize pumps, so we can feed soda ash to the NaCN if needed. Also electrical sockets for the portable sump pumps.
Note on J365: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. pH measurement, Fan for gases and fumes and sump pump
Note on J366: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gas Alarm. Fan for gases and fumes and sump pump
Note on J368: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electrical sockets for the portable sump pumps.