Terms of Reference

for Test Carrying out, Delivery of Device, Developing of Project Documentation, Installation  and Commissioning the Devices

| Client | RICH METALS GROUP |
| --- | --- |
| Facility (construction site) | Dry waste storage, thickening node |
| Address: | Georgia, Kazreti |
| Construction type | Production modernization |
| Production work mode | Day and night, during the whole year |
| Purpose of the activities | - Evaluation and selection of optimal flotation tailings thickening technology; - Reduction of flocculant consumption; - Reduction of moisture in bulk cake. |
| Delivery volume | The scope of delivery shall include all services and equipment required for the full functioning of the facility to achieve the technological performance indicators specified in this technical specification. Including: –Conducting test trials at the customer’s site using two technologies for thickening flotation waste. These are classical thickening in thickeners and combined technology using hydrocyclone units; – Development of technical documentation based on the results of test trials; – Development of equipment specifications with determination of their prices, planned terms of manufacture and delivery; – Purchase and delivery of equipment; – Commissioning and commissioning works; – Commissioning of the facility; – Training of customer personnel. The equipment must be new, no earlier than 2024. |
| Documentation requirements | - All materials provided to the Customer must be presented in Russian using the metric system of measurement and the International System of Units (SI); - The documentation shall be delivered to the Client in 2 copies in printed form and 1 copy of the electronic version. The electronic version shall be executed in Microsoft Office (Word and Excel) softwares, drawings – in Acrobat Reader program, and drawings – in AutoCAD software. - The supplier shall submit documentation containing the following information, but not limited to: – Technological schemes; – Description of technologies; – Specifications of equipment and materials; – Catalog of spare parts; – Survey sheets; – Operation manual; – Instructions for installation, maintenance and repair; – General view drawings; – Drawings for equipment assembly; – Electrical connection diagrams; – Specification of electrical equipment; – Instructions for operation, installation and maintenance of electrical equipment; – Drawings for cable routing; – Drawings for assembly of electrical equipment; – Principle diagrams; – Single-line electrical diagrams; – Characteristics and consumption of chemical reagents; – Estimate of capital and operating costs for the facility; – Certificates of conformity of the supplied equipment, quality certificates; – List of auxiliary equipment, products and materials to be provided by the customer (if any). |
| Automation requirements | The supplied equipment must include the necessary measuring instruments (transducers) and control elements (switches, regulators and actuators) that ensure the operation of the equipment within the given technological parameters by connecting them to the automated process control system (ACS) of the enrichment plant. |
| Supplier guarantees | The Supplier guarantees the quality of the supplied technological equipment and its warranty service for a period of 24 months from the date of delivery or 18 months from the date of commissioning, whichever comes first. |
| Requirements for the submission of technical and commercial documentation | - Preliminary technological, water-sludge schemes, design solutions; - Preliminary estimate of capital and operating costs; - Preliminary list of auxiliary equipment, products and materials (limits of liability) that the customer must provide (if any); - Brief description of the research methodology, hardware design of the tests; - Confirmation / clarification of the warranty indicators; - Fixed price, cost calculation must be provided. |
| Initial Data |  |
| Productivity | 900-1400 მ3/სთ |
| Solid content | 18;25% |
| Solid specific gravity | 2,7-2,9 ტ/მ3 |
| Granulometric distribution | Thickness classes, (μm); Output, %. –; +; %. 200,0; 1,70. 200,0; 140,0; 4,80. 140,0; 100,0; 6,75. 100,0; 71,0; 8,10. 71,0; 44,0; 7,65. 44,0; 32,0; 5.90. 32,0; 16,0; 12,80. 16,0; 8,0; 24,10. 8,0; 0,0; 28,20. 100,00. |
| pH | 8-12 |
| Warranty Indicators |  |
| Solids content in the filter feed,% | Not less than 55 (combined product: sands hydrocyclone + thickening) |
| Purity of thickening agent, mg/l | Not more than 200 |
| Reduction in total flocculant consumption, g/t on ore processed | At least 70% of the initial cost (to be specified during the testing process), for preliminary calculations, the initial cost should be taken as 40 g/t |

Phases and terms  for work completion

| Phase |  | Term of completion* | Activity content |
| --- | --- | --- | --- |
| 1 | Waste testing | 2 weeks | - Conducting tests of various types of ore processing unsorted waste in order to determine the main technological indicators: granulometric composition, optimal density for thickening, optimal type of flocculant, purity of the sediment, and the degree of achievable thickening. - Calculation of the output parameters of hydrocyclones and modeling of hydrocyclones discharges based on the obtained calculations. - Conducting hydrocyclone screening tests to determine key technological indicators when processing various types of ore. - Comparison of testing indicators and justification of optimal thickening technology. |
| 2 | Technology Agreement | 1 Week | - Agreement with the client on the thickening technology acceptable for design. - Development of design solutions and agreement of the resulting option with the client. |
| 3 | Engineering | 2 Weeks | - Development of a technological scheme of the thickening section. - Calculation, selection of technological devices and agreement with the client. - Development of a control scheme, selection of equipment for an automated hydrocyclone device. - Calculation of the main technological indicators of the thickening section. - Placing an order for the placement of equipment. Agreement with the customer. |
| 4 | Design | 3-7 Weeks | - Development of design documentation. - Agreement with the client and approval of design solutions. |
| 5 | Implementation of design solutions |  | - Equipment delivery. - Installation and repair works. - Commissioning works. - Commissioning (72 hours of continuous operation at 100% of the design load). |

* The tenderer specifies the terms.

The total project implementation time (from testing to implementation) is 2-3 months (excluding   commissioning-maintaining works).