# THE REGIONAL ENVIRONMENTAL CENTRE FOR THE CAUCASUS

# Terms of Reference

Knowledge Management Expert for Development of Guidelines on Sustainable Management of Pasturelands within Emerald Sites of Georgia

Publication Reference Number: 076/RECC/G/UNEP-05-2025

| Contract Title: |  | Consultancy Service Contract for Development of Guidelines on Sustainable Management of Pasturelands within Emerald Sites of Georgia |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Type: |  |  | Fee-based |  |  |  |  |
| Contracting Organization: |  |  | The Regional Environmental Centre for the Caucasus (RECC) |  |  |  |  |
| Division/Department: |  |  | RECC Projects’ Implementation Unit |  |  |  |  |
| Programme/Project Number: |  |  |  | „Transforming Policy and Investment through Improving Ecosystem Management and Restoration of Degraded Drylands of Dedoplistskaro Biosphere Reserve in Georgia to Generate Multiple Environmental and Socio-Economic Benefits“ (GEF Project ID: 11141) |  |  |  |
| Duty Station: |  | Tbilisi, Georgia |  |  |  |  |  |
| Expected Start Date of Assignment: |  |  |  |  | May, 2025 | Duration: | 3 months (up to August 2025) |
| Estimated Number of Working Days: |  |  |  |  | 20 Working Days |  |  |
| Reports to: | Sophiko Akhobadze |  |  |  |  | RECC Executive Director |  |

I. Background

The Global Environment Facility (GEF)-funded project “Transforming Policy and Investment through Improving Ecosystem Management and Restoration of Degraded Drylands of Dedoplistskaro Biosphere Reserve in Georgia to Generate Multiple Environmental and Socio-Economic Benefits” supports ecosystem restoration, biodiversity conservation, and sustainable land use in the Dedoplistskaro Biosphere Reserve.

The project is implemented by the United Nations Environment Programme (UNEP) and executed by the Regional Environmental Centre for the Caucasus (REC Caucasus) on behalf of Georgia’s Ministry of Environmental Protection and Agriculture (MEPA). It runs for four years starting in 2025.

Project component 1 aims to create an enabling environment for integrated and collaborative planning and management of Dedoplistskaro BR, contributing to sustainable land management and biodiversity conservation. Component 1 will provide technical guidance and support for sustainable management of the biosphere reserves, based on scientific data and knowledge and best practices. Development of the technical guidelines, manuals, standards, and norms for sustainable management of the Biosphere Reserves is prescribed under the output 1.1.3 of the Component 1.

The territory of the Dedophlistskaro Biopshere Reserve (DBR) encompasses sites designated within the country’s Emerald Network for the preservation of Europe's wild flora, fauna, and their natural habitats. Both Vashlovani Protected Areas and Chachuna Managed Reserve located within the DBR are part of the Emerald Network sites. Simultaneously both Emerald sites have traditionally served as winter pastures.

Overgrazing is serious threat to the environment on the project area, with over 300,000 sheep grazing in the DBR, in addition to cattle and horses.  Seasonal grazing by sheep is a cultural practice engrained in local shepherds and which is leading to over grazing of pastures resulting in plant cover becoming degraded, exposing the soil, and making it more vulnerable to erosion. In addition, overgrazing poses a significant threat to the biodiversity of the Emerald Sites.

Sustainable management of pastures within the Emerald Sites, in accordance with the requirements of the Bern Convention, is particularly important to reduce pressure on biodiversity. In order to share best international knowledge and practices in this regard, the project will support the development of a Guidelines for Sustainable Management of Pastures within Georgia’s Emerald Sites under the component 1. The Technical guideline will assist decision-makers and local users in improving existing pasture management practices and planning pasture use so that damage to biodiversity from unsustainable grazing is minimized and/or prevented. The Guidelines for Sustainable Management of Pastures within Emerald Sites will also be widely used at the national level, as significant areas of grasslands are represented within the Emerald Areas of Georgia, a large part of which is used as pastures.

II. General Objective of the Assignment

The Knowledge Management Expert provides consultancy services of technical assistance for development of the Guidelines for Sustainable Management of Pastures within Georgia’s Emerald Sites.

He/She will work under the overall guidance and supervision of the RECC Executive Director (Project Director/Supervisor) and the Biodiversity & Ecosystem Restoration Lead Expert (RECC Project Core Team Coordinator).

III. Scope of Work

The consultant’s tasks under the present assignment will include:

a. Overviewing Georgia’s Emerald sites

Provide brief characteristic of Georgia’s Emerald sites with particular emphasis on those designated to protect various rangelands/grassland habitats. Use the existing information about Emerald sites (Emerald database, Emerald Viewer, national sources) to identify which Emerald sites include which Bern Convention Resolution No. 4 (1996) rangeland/grassland habitat types, and what is the protection status of these Emerald sites.

b. Identifying challenges faced in management of Emerald sites

Explain how Emerald sites are managed within and outside nationally designated protected areas, identify challenges and difficulties faced in administration of Emerald sites, provide general assessment of natural resources’ use within Emerald sites with particular emphasis on use of grasslands as pastures, Identify threats and pressures for rangelands/grasslands habitat types present in Emerald Sites of Georgia.

c. Analysing existing guidelines and practices of pasturelands management in Natural 2000 sites

Source and review guidelines, management plans, and any other advisory/regulatory documents for pasturelands management that are developed and used for the protection and sustainable use of grasslands in Natura 2000 sites in the European Union. Identify elements in such documents that are relevant for and compatible with the main principles of Emerald sites’ management in Georgia.

d. Drafting guidelines for Sustainable Management of Pastures within Emerald Sites

Based on the collected information and undertaken analyses, draft Guidelines for Sustainable Management of Pastures within the Emerald sites of Georgia to be used by pastures management practitioners for the application in Emerald Sites to prevent/reduce pressure on grassland habitats.

The Guidelines for Sustainable Management of Pastures within the Emerald sites of Georgia may include, but not limited to, the following aspects:

- Background information on Emerald Network development;

- Analysis of experience in Emerald sites’ management in Georgia with emphasis on grasslands: patterns, challenges, areas for improvement;

- Overview and analysis of grasslands/pasturelands management guidelines/regulations and practices applied in Natura 2000 sites in the EU;

- Guidelines for Sustainable Management of Pasturelands within Emerald sites of Georgia.

e. Undertaking stakeholder consultations on the draft Guidelines

Undertake individual and focus group meetings with key stakeholders on the draft Guidelines. Agencies to be met would include but not be limited to the Biodiversity and Forestry Department and Melioration and Land Management Department of the Ministry of Environmental Protection and Agriculture, Agency of Protected Areas and National Agency for Sustainable Land Management and Land Use Monitoring under this Ministry.

IV. Reporting Obligations: Deliverables and reporting Schedule

The Expert for Development of Knowledge Materials will submit reports (in electronic format) to the following deliverables in Georgian Language:

| Report Index | Name of Deliverable/Means of Verification | Time of Submission |
| --- | --- | --- |
| R1 | Detailed outline of the Guidelines for Sustainable Management of Pasturelands within Emerald sites of Georgia | May, 2025 |
| R2 | Draft the Guidelines for Sustainable Management of Pasturelands within Emerald sites of Georgia | June, 2025 |
| R3 | Final version of the Guidelines for Sustainable Management of Pasturelands within Emerald sites of Georgia | July, 2025 |

V. Payment Schedule

The Expert for Development of Knowledge Materials shall submit to the RECC the reports in the form and within the time periods specified in Table 1 (Reporting Obligations) as per Terms of Reference, acceptable to the RECC. The payment mode for the service will be applied based on delivered reports and acts of acceptance (Service Delivery Acceptance Acts) signed by both sides (RECC and the Expert for Development of Knowledge Materials) and submitted by the Expert of original invoices to the RECC.

RECC will only make milestone payment based on achievement of specific deliverables as specified in time schedule for submission of deliverables as per Table 1 (Reporting Obligations).

The schedule of payments and estimated time input are specified below:

Table 2. Schedule of Payments and Estimated Time Input

| Report Index for Deliverables | Estimated Number of Working Days | Amount of Transfer | % of total contract ceiling for the Services (total Value of the Service) |
| --- | --- | --- | --- |
| R1 | 5 | Number of working days x Working day rate | 25 % |
| R2 | 10 | Number of working days x Working day rate | 50% |
| R3 | 5 | Number of working days x Working day rate | 25% |
| Total | 20 | 20 working days x Working day rate | 100 % |

VI. Qualifications and General Professional Experience

  - Advanced degree (Master’s or higher) in biodiversity conservation, restoration ecology, natural resources management, or related environmental fields.

  - Minimum of 5 years of experience in technical roles related to biodiversity, pasturelands management, Emerald sites management, land use planning, or protected area management.

  - Proven experience in development of knowledge materials, including technical guidelines in field of biodiversity conservation, restoration, land use planning, protected areas management, pasturelands management.

  - Proven experience in providing expert input to multi-stakeholder development projects.

  - Familiarity with international donor-funded project requirements (GEF/UNEP experience preferred).

  - Excellent interpersonal skills and the ability to facilitate technical dialogue with a wide range of stakeholders.

Fluency in Georgian and English (spoken and written) is required.

VII. Award Criteria

Evaluation will be made in accordance with the quality/price-based selection method per REC Caucasus procedures and rules. The best value for money will be established by weighing technical quality against price on an 80/20 basis.

The quality of each technical offer will be evaluated in accordance with the award criteria and the associated weighting as detailed in the evaluation grid specified in Annex 1 of this Terms of Reference.

Annex 1. Evaluation Grid

| Ref. Number: 076/RECC/G/UNEP-05-2025 Knowledge Management Expert for Development of Guidelines on Sustainable Management of Pasturelands within Emerald Sites of Georgia |  |
| --- | --- |
| EVALUATION GRID | Maximum |
| Organisation and Methodology |  |
| (Max 30 points) |  |
| Rationale | 5 |
| Strategy | 5 |
| Timetable of activities | 10 |
| Total score for Organisation and methodology | 20 |
| Expert |  |
| (Max 70 points) |  |
| Qualifications and skills |  |
| Adequacy of Educational background for tasks | 10 |
| General professional experience |  |
| At least 5 years of experience in technical roles related to biodiversity, pasturelands management, land use planning, or protected area management | 10 |
| Specific professional experience |  |
| Familiarity with Emerald sites network and specific Knowledge of Georgia’s Emerald sites | 10 |
| Experience in performing of analytical work in the field of nature resource management, including pasturelands management | 15 |
| Proven experience in development of knowledge materials, including technical guidelines in field of biodiversity conservation, restoration, land use planning, protected areas management, pasturelands management | 15 |
| Proven experience in providing expert input to multi-stakeholder development projects and familiarity with international donor-funded project requirements | 10 |
| Specific Qualifications and skills |  |
| Writing and communication skills in Georgian and also strong interpersonal and general communication skills, strong cultural sensitivity and ability to work in multi-cultural environments; Basic knowledge of written and oral English language (Good knowledge of written and oral English language as an asset) | 10 |
| Total score for Expert | 80 |
| Overall total score | 100 |