Annex 1

Terms of Reference

Information Campaign to Raise Awareness in Georgian Society on Trafficking in Persons and Promote Concerted Preventative Action

- Introduction

The Mission to Georgia of the International Organization for Migration (IOM), United Nations Migration Agency, invites interested parties/service providers to submit proposals to partner with IOM for the design and production of an information campaign dedicated to raising the awareness of specific target groups about the risks of trafficking in persons (TIP) and empower them with knowledge to take preventive action for the benefit of themselves and their peers.

These terms of reference provide the details of the products to be delivered to IOM and is an official attachment to the Request for Quotation released by IOM.

A multi-media campaign will be implemented at Georgia’s busiest hubs, which may include metropolitan transportation grids, bus and train stations, international airports, Public Service Halls and other hubs in Georgia’s infrastructure where significant movement of people takes place on a daily basis.

Audio-visual and graphic ads will be produced in various forms for display on national media outlets, on social media platforms and in various means of transportation. This campaign will convey two separate messages:

- A call on the population of Georgia and foreign visitors to: a) be aware of the dangers of TIP, b) cooperate with the Georgian authorities in reporting instances of TIP and c) for possible victims to contact referral services and access low-threshold and confidential identification support services.

- As a separate component of the campaign, focus will be on the plight of children who are exploited in street begging and other forms of human trafficking and will include an appeal on society to cooperate in eradicating trafficking in children.

The messages and visuals will avoid stigmatization, stress positive communication approaches rather than portraying TIP in a fear-instilling way, but relaying at the same time that TIP affects everybody and combating it is a collective responsibility.

This campaign is part of the following project that IOM implements in Georgia, namely:

- “Joining Forces to Combat Trafficking in Persons in Georgia (JFC-TIP, IOM reference: PX0503)”, funded by the International Bureau for Narcotics and Law Enforcement Affairs (INL) of the US Department of State.

The duration of the campaign is expected to last from early September until mid-December 2025 (up to 4.5 months).

- Overall objective of the information campaign

The overall objective of this information campaign is to increase awareness and knowledge levels of the relevant target groups of the information campaign about the principal aspects of TIP and to empower the target groups to use that knowledge for the protection of the rights of themselves and other persons.

- Relevant target groups of the information campaign

- Society at large in Georgia, including an appeal to come forward and contact relevant bodies/organizations to report when they witness a possible instance of TIP.

- Women, girls, men and boys from disadvantaged urban and rural areas in Georgia, who live in difficult socio-economic circumstances and who may find it hard to judge the veracity and authenticity of job offers, in particular when this concerns employment abroad.

- High-school pupils between the age of 16 and 18 and students of tertiary educational institutions, who are at a critical junction in life when making decisions concerning their professional career.

- Tourists and other visitors who come to Georgia for leisure and business.

- Migrant workers who come from foreign countries to work in Georgia, especially those employed in Georgia’s informal economy and those working without official work contract and lacking information and access to adequate mechanisms to protect their rights.

- Purpose of the information campaign

Thanks to the TIP multi-media campaign, society at large and specific target groups have:

- Increased their awareness about the criminal behaviour of those persons, who are responsible for the exploitation of women, girls, men and boys in various manifestations of TIP.

- Appreciated the particular aspects of trafficking in children and why giving financial aid to children does not help them, but rather sustains their exploitation in forced begging.

- Been empowered to critically assess job offers and avoid possible exploitation.

- Received the clear message to act when witnessing a possible TIP case by reporting to the hotlines indicated on the campaign material.

- Indicators to measure successful implementation of the information campaigns

- Numbers of locations at which campaign material is displayed/disseminated.

- Number of outreach and awareness raising events organized or supported.

- Number of participants in awareness raising and outreach events/initiatives.

- Number of views/likes/shares of relevant campaign material on social media.

- Number of people passing through major transportation hubs where campaign material has been displayed.

- Number of TIP-related calls entered at the hotline services that are indicated on the campaign material.

- Report produced on the assessment of the impact of this information campaign.

- Required Deliverables and Implementation Modalities - tangible and measurable outputs

The selected service provider will supply IOM with the following products and services. The designs of all below-mentioned products should be consistent and carry relevant logos in coordination with IOM:

- Design of two posters/banners fit for placement in high-quality display holders as commonly used at transportation and public congregation hubs in Georgia. The banner will contain key messages in multiple languages and relevant hotline numbers. The design should be specifically targeted on TIP, be impactful, yet balanced.

- The first poster/banner shall contain generic information and warning messages about the dangers of TIP.

- The second poster/banner shall contain specific information related to child trafficking, including advice to society not to give money to begging children, but rather show empathy, give food or clothing, and report the crime to police.

Requirements:

- Each poster/banner shall contain two language versions, as follows: front side: Georgian-English together; back side: Russian-Turkish together.

- Size: based on commonly used measures of display frames in suggested locations.

- Other: full colour design, use of high-density illustrations.

- Print and display 24 posters/banners in 12 high-visibility locations

The locations mentioned below are merely suggestions. The interested service provider is encouraged to suggest other venues for display of the poster/banner if those are deemed more impactful and/or cost-effective:

- One or more of Georgia’s international airports, with the following specifications: a) luggage reception area in the arrival hall, b) check-in area in the departure hall.

- The entry hall of Georgia’s Border Crossing Point (BCP) in Sarpi.

- Public Service Halls in major cities.

- Tbilisi Underground stations and/or carriages.

- Bus stops in Georgia’s major urban agglomerations with high passenger flows.

The poster/banner shall be placed in high-quality display frames (see below illustrations as examples).

- Required duration of placement: please provide two price quotes for placement of the poster/banner in 12 locations, for a period of a) 2 months and b) 4 months respectively.

- The selected service provider is expected to negotiate with the management authorities of all selected locations the conditions for placement of the poster/banner, obtain competitive price quotes and pay for those services.

- Two animated video clips reflecting the two main messages of the campaign, namely i) general message on the dangers of TIP, and ii) specific aspects of child trafficking. The general requirements of these products are:

- IOM requires two animated (“graphic”) video clips, in Georgian language version (“voice-over”) with English subtitles. The duration of the clip shall be at least 30 seconds and last no longer than 1 minute.

- The design of the clips shall be consistent with the design of the poster/banner.

- The format of the clips shall enable use on social media as well as placement on any other media outlets.

- IOM requires the design and printing of 50,000 flyers (maximum two-fold A-5 size paper printed on matte paper of at least 150 grs. in full-colour), based on the design as produced for the two posters/banners and containing the same content in the four languages as indicated under point 6.a) above.

The print run of these two flyers shall be equally distributed (25,000 copies each) over two versions dedicated to: i) generic risks of TIP, and ii) specific aspects of trafficking in children.

  - Multimedia Approach: Leverage digital media for broader engagement. The goal is to develop content that is visually appealing, informative and shareable across various social media platforms. Social media ads should run for a duration of one month on the following platforms: Facebook, LinkedIn, YouTube and Instagram. The campaign's success will be measured using metrics such as reach, impressions, engagement and click-through rates. The ads should achieve a minimum reach rate of 50,000 users per platform. The vendor is responsible for ad creation, placement, monitoring and optimization, ensuring compliance with platform-specific policies and brand guidelines. Regular performance reports should be provided to track progress and make necessary adjustments.

- Creative collaboration with established artists

  - Engage a renowned and experienced artist or painter to develop a painting or a series of paintings that depict the issue of street begging affecting children. This artwork can be created both graphically and physically, providing versatile options for use during the campaign. Given the sensitivity of the subject, it is advisable to avoid using real photos of children engaged in street begging. Instead, a more creative and illustrative approach would be desirable. The artist's work should evoke empathy and raise awareness about the issue without compromising the dignity of the children. The selected artist should have a significant following and a strong presence in their field, which can be leveraged to disseminate the campaign message more effectively. Additionally, the illustrations created can be used to produce various merchandise or visibility materials, further extending the reach and impact of the campaign.

or

  - Creative Collaboration with a Film Director: Collaborate with a skilled film director to produce a short film, no longer than 5 minutes, that portrays the poignant story of street begging among children. The film can be either animated or graphical, depending on the director's expertise and the campaign's needs. The scenario should address common misconceptions about street begging and be crafted to touch the audience's emotions, creating a sentimental and impactful narrative that raises awareness and fosters a deeper understanding of the issue. The film should resonate with viewers, encouraging them to reflect on the plight of children involved in street begging and inspiring them to support the campaign's objectives.

- Organize the outdoor launch of the information campaign

As soon as the deliverables under above points a) to d) have been produced and are physically available, the selected service provider, in close coordination with IOM, shall organize the launch of the information campaign in a prominent outdoor location in Tbilisi (in a public space such as a park or square), with the aim to attract maximum public attention to IOM’s information campaign. The posters/banners will be displayed as exhibition stands, the videos will be shown on a screen and the flyers distributed among the attendees. The selected service provider will also be responsible for inviting media representatives to attend and report on this official launch of the campaign.

Other requirements

As concerns the campaign’s concept, all messages and visuals will be presented in a gender-balanced manner, avoiding stigmatization, stressing positive communication approaches rather than portraying trafficking in human beings in a fear-instilling way, but relaying at the same time that trafficking in human beings affects everybody and combating this crime is a collective responsibility.

This campaign will carry various messages, inter alia a call on the population and foreign visitors to cooperate with the Georgian authorities and civil society organizations in reporting instances of TIP and for possible victims to offer low-threshold and confidential identification and referral services.

The main slogan of the campaign on trafficking in persons can be one or more of the following versions. Interested applicants submitting a proposal under this RFQ can obviously propose any other slogan as they deem fit – the below examples are merely for illustrative purposes and interested service providers are encouraged to propose any other slogan they deem effective:

“Exploiting People is a Crime… Fighting it is a Duty.”

“Don’t Give Money to Children Begging on the Street – Your Petty Cash Only Sustains the Traffickers!”

The material to be produced will contain hotline numbers of relevant actors, which may be state bodies that operate specialized trafficking hotlines, hotlines or dedicated social media groups operated by civil society organizations and IOM.

- Scope of work

IOM is looking to partner with a socially responsible, creative entity that has experience in storytelling, advocacy and implementation on national level (with a focus on Tbilisi, Kutaisi, Batumi) multi-media awareness-raising campaigns, using data, communication and technology as well as behavioral science.

IOM invites interested parties/service providers to apply with a letter of interest, outlining the vendor’s understanding of the assignment, their relevant experience, and their proposed approach to fulfilling the project requirements.

For further details please refer to the Request for Quotation, of which this document is an official annex.

For example, as measured by the number of people crossing the border at airport and land border crossing points.

This impact assessment is not part of these terms of reference, but will be rather conducted by a specialized company, which will be selected through a separate procurement process.