VOLUME 2

SECTION 3

SPECIAL CONDITIONS

# CONTENTS

# These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Other special conditions should be indicated afterwards.

Article 2	Language of the contract

2.1	The language used shall be English and/or Georgian.

Article 3	Communication

3.1	All communications related to the present Contract shall be made in written form referring the contract Title and publication identification number and must be sent in English and/or Georgian by mail courier, e-mail or by hand to the following addresses:

Contracting Authority:

# Energy Efficiency Centre Georgia (“Energoefeqturoba Centri Saqartvelo”)

Office #611, IV Floor, 19 D. Gamrekeli street, Tbilisi 0160, Georgia

# Contact Details:

# Name: Diana Bichelashvili

# Title: Key Procurement Expert

# Name: Elene Gvilava

# Title: Team Leader

# Email: Tenders.EECGEO@yahoo.com

3.2	An electronic system will be used by the contracting authority and the contractor for all stages of implementation including, inter alia, management of the contract (amendments and administrative orders), reporting (including reporting on results) and payments.  The contractor will be required to register in and use the appropriate electronic exchange system to allow for the e-management of the contract.

The electronic management of the contract through the aforementioned system may commence on the date on which implementation of the contract starts, as described in Article 33 of the general conditions to the contract, or at a later date. In the latter case, the contracting authority will inform the contractor in writing that he will be required to use the electronic system for all communications within a maximum period of 3 months.

Article 4	Supervisor and supervisor’s representative

4.2	Under this contract, the supervisor does not delegate his duties and authority to a supervisor's representative

4.3. The Contracting Authority shall have right to: inspect the quality and progress of Work at any time at its discretion, to change the scope of Work and to give mandatory instructions to the Contractor; appoint the construction supervisor/s (the “Works Supervisor”) and to delegate any and all rights and duties of the Contracting Authority, including, but not limited to the right to give the Contractor any verbal and/or written instructions related to Works, while remedying the shortcomings and defects and/or during the Warranty Period.

Article 5	Access to the site

5.1	The contractor is reminded that there is a head of delegation of the European Commission in the state of the contracting authority. The contractor is obliged to give the head of delegation free access to its sites, factories, workshops, etc., and generally assist the head of delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the head of delegation.

All correspondence between the contractor and the contracting authority or project supervisor must be copied, for information, to the head of delegation of the European Commission at the following official address:

EECG – Union Energy Efficiency Centre Georgia

Office № 611, VI floor, 19 D.Gamrekeli Str; Tbilisi 0160; Georgia

Article 6	General obligations

6.1. General conditions for the construction works

Prove, warn and advisory obligation of the Contractor during project implementation

The Contractor is obliged to inform the Contracting Authority in written form about circumstances that could lead to defects or damages. This obligation applies not only on the services and works implemented by the Contractor himself, but also on services and works implemented by other companies on the construction site he is aware of.

Information about the construction site during the tender preparation

The Contractor is obliged to inform himself about the situation on the site (e.g. access to the site, access to the installation areas, infrastructure, connections with electricity, fresh water, sewage, etc.)

Actual measurements

The Contractor is obliged to take on site measurements and comparing the measurements with provided plans and documents. In case of deviations, the Contractor must inform the Site Supervision and the Contracting Authority in written form before starting the implementation.

Access to the site, streets, damages, cleaning during project implementation

The Contractor has to organize and to coordinate the access to the construction site. Costs for damages should be borne by the Contractor. The construction site has to be cleaned periodically (once a week)

Power, fresh water, sewage, toilets

Access to electricity: The Contractor has to organize and prepare a central access (main distributor) to electricity in consultation with the Municipality or Project Team. The costs for electricity should be borne by the Contractor.

Access to fresh water: The Contractor has to organize and prepare a central access to fresh water and to install a fresh water meter in consultation with the Municipality or Project Team. The costs for fresh water should be borne by the Contractor.

Access to sewage system: The Contractor is obliged to respect the relevant regulations and requirements on the site.

Toilets must be provided and maintained by the Contractor (if needed).

Survey of the existing situation (surfaces, etc.)

The Contractor must take evidence of the construction site prior to the construction works (i.e. photo documentation, description of the defects). The document should be signed (and a copy provided to) by the following parties: Contractor, Project Team or Municipality.

Safety regulations (incl. fire safety)

The Contractor has to respect all national safety regulations. He is responsible for providing all required safety equipment for workers to prevent accidents.

Project Manager of the Contractor

A responsible project manager must be available at the site during the entire construction period.

Job meetings

The Contractor is obliged to participate in all meetings arranged and coordinated by the Site supervision, Project Team or the Municipality. Job meetings will be scheduled weekly during the construction period.

Representatives of the following parties shall participate in the meetings: Municipality, Contracting Authority, Site Supervision, Contractor’s Project Manager, Facility/Institution, Project Design Company (on demand) and other interested parties.

The purpose of the job meeting is to assure proper coordination, determine construction progress, monitor progress and update the implementation schedule, review requisitions and change orders, expedite completion of the project in accordance with the contract documents and review other relevant items.

Construction weekly reports

The Contractor is obliged to note all relevant information in a weekly report which must be provided to the municipality, project team and the Support Team not later than Tuesday next to the reporting period.

The following information must be noted by the PM (data shall cover full info occurred on daily basis when appropriate):

- Number of workers on the site on daily basis

- Number of working hours on daily basis

- Work done in accordance to the bill of quantity on daily basis

- Weather condition on site (rain, temperature)

- Delivery of materials on the building site on daily basis

- Visits to the site: name, function on daily basis

- Meetings on site on daily basis

- Incidents

- Others

The template for the weekly report is attached at the end of this document (Annex to be provided upon request). The submission of weekly reports, revision, comments or written confirmation shall not be the basis of payment.

The Contracting Authority is entitled to suspend further payments if above mention reports are not submitted.

Changes of services and works during the construction – Change Order

The Contracting Authority is entitled to change the contracted services and works by a Change Order. The Contractor has to submit his Change Proposal prior to the implementation of the works and services. The Contractor shall include detailed breakdowns of labor and materials for all trades involved and the estimated impact on the implementation schedule. The offer must be approved by the Contracting Authority prior to the implementation.

Works and services implemented without written approval by the Contracting Authority cannot be invoiced.

In case of significant changes in the technical design, these changes must be approved by the Support Team.

Samples to be approved

The Contracting Authority is entitled to demand samples of equipment and materials which are planned to be installed by the Contractor. Those equipment and materials must be approved by the Contracting Authority prior to the installation. Costs should be borne by the Contractor.

List of products

The Contractor is obliged to provide a list of the products (product, type, manufacturer, place of installation) which will be installed latest 2 weeks after signing of the contract. The list must be approved by the Contracting Authority and Site Supervision.

Ancillary works and services to be included in the unit prices (without additional compensation)

All unit prices include all costs for personal and materials, which are required to deliver a turn key project. In particular the following must be included:

- Site overhead (if not otherwise stated)

- Effective safeguards of the entire construction site to avoid accidents (if not otherwise stated)

- Effective protection of materials against theft

- Define a geodesic fix point level (i.e height indicator for building construction)

- Prices are valid for works and services without any difference of levels, heights and depth for the entire construction site (if not otherwise stated)

- Effective preservation measures against wind, rain, snow, frost, etc. In case damages occur even if the Contractor had foreseen preservation measures, the Contractor is 	obliged to remove barriers that hinders the continuation of works and repair damages without any additional compensation

- All unit prices for the offered works and services must include all required materials, delivery, installation, fixing materials, testing, cutoffs and broken materials

- Participation of job meetings

- Maintaining the construction site logbook

- Difficulties due to weather conditions (snow, wind, rain, ice, etc.)

- Difficulties due to the delivery the works and services in sections (to maintain the facilities/institutions operation)

- Certificates for materials

- Requested samples of materials and installation procedures

- All required documents, calculations and measurements for invoicing

- All design services which are required for the construction and installation (if not otherwise stated)

- Documents which are required for the authorities (certificates, attests, documents, etc.) (if not otherwise stated)

Quality control visits by the Support Team

The quality of the construction works will be assessed by the Support Team for relevance to the technical design and best European practices in order to secure the sustainability of the implemented measures. The Contractor must address all defects mention in the Support Team’s report in 10 days and duly inform the Contracting Authority and the Support Team.

Taking into operation parts of the works and services

The Contracting Authority is entitled to take in operation parts of the finalized work prior to the final acceptance. This does not affect the final acceptance procedure of the entire works and services described below.

Final acceptance

The final acceptance has to be carried out in following manner:

1) The Contractor informs the Contracting Authority in written form about the completion of the project

Installations which are not visible any more at the time of the final acceptance (i.e. district heating pipes, covered heating pipes, electric cables works) shall be approved by the Site Supervisor prior to the finalization of such works. The Contractor is obliged to inform the Site Supervision in due time for the approval of such works.

2) The Contracting Authority organizes a meeting at the construction site with the following participants: Contracting Authority, Municipality, Project Team, Site Supervision, Contractor, Facility/Institution, Support Team (or expert provided by Support Team) and other relevant parties. During this meeting the finalization of the services and works will be verified. Major construction defects or any other major deviation from the agreed services and works will be recorded (pictures, minutes, etc.). The list of construction defects will be signed by all parties at the end of the meeting.

3) A list of construction defects incl. deadlines for their correction will be handed over to the Contractor by the Contracting Authority.

4) After correction of the construction defects, the Contractor has to inform the Contracting Authority in written form about the completion.

5) The Contracting Authority organizes a meeting at the construction site to verify the corrections of the construction defects. In the event that all defects have been corrected the final acceptance protocol will be signed by all parties.

In the event of conflicts between the project documents, the following sequence shall be agreed:

- Contract incl. general terms of condition

- Technical drawings and schemes

- Bill of Quantity incl. Annex (detailed descriptions)

Article 7	Performance guarantee

7.1	The amount of the performance guarantee will be 5% of the amount of the contract and any addenda thereto.

Article 8	Liabilities and insurance

8.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

8.1 b)	By way of derogation from Article 16.1, b), paragraph 2, of the general conditions, compensation for damage resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

Article 9	Programme of implementation of tasks

9.1	The contractor shall provide the supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the contractor proposes to carry out the works, and shall be based on the tranches foreseen in Article 49.1 of the special conditions.

9.2. 	The supervisor shall return this document to the contractor with any relevant remarks within 10 days of receipt, save where the supervisor, within those 10 days, notifies the contractor of its wish for a meeting in order to discuss the documents submitted.

Article 10	Exceptional risks

10.1	No any exceptional weather conditions applicable

Article 11	Period of implementation of tasks

# 11.1	the Period of implementation of the whole scope of works comprises of 5(five) months.

Article 12	Delays in the implementation of tasks

12.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 13	Work register

13.1	The contractor shall prepare the construction log-book according to the national legislation

Article 14	Origin and quality of works and materials

## 14.1	All goods purchased under the contract must originate in any eligible source country as defined in Regional Programme in the Eastern Neighbourhood in support of the Eastern Partnership Flagship Initiative on Sustainable Municipal Developmentowever, the goods to be purchased may originate from any country, whenever the total price of the estimated quantity of those goods, as reflected in a separate item of the breakdown of the lump-sum price (Volume 4.2.3) is below EUR 100 000. A category of similar goods to be purchased shall not be broken down over more than 1 item of the breakdown of the lump-sum price (Volume 4.2.3)]

## For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

14.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*)	the following specifications as defined in Technical Designs and BoQ

(*)	the requirements of General conditions for the construction works

14.3	All material and equipment provided during thermal refurbishment works should comply to the preliminary agreed quality, brand and description between the parties.

Article 15	Ownership of plant and materials

15.2	The equipment, temporary structures, plant and materials on the site shall for the duration of the execution of the works, be vested in the contracting authority.

Article 16:	General principles for payments

16.1	Payments shall be made in GEL .

16.2	If invoices are submitted to the contracting authority, the contractor shall inform the the contracting authority  by sending a copy to el. Mail:  info@eecgeo.org 44.3	By derogation, pre-financing payment to the contractor for the lump-sum advance shall be made within 30 days. Other pre-financing payments to the contractor shall be made within 60 days. Interim payments to the contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 60 days, and the final payment to the contractor of the amounts due after the final statement of account issued by the supervisor shall be made within 60 days.

Article 17	Pre-financing

17.1	The only pre-financing granted to the contractor, is the lump sum advance referred to in Article 46.1(a).

17.2	By derogation to Article 46.2 of the general conditions, the lump sum advance referred to in Article 46.1(a) shall be 20% of the original contract price.

17.3(c)	By derogation to Article 46.3(c) of the general conditions, no pre-financing guarantee is required.

17.8	The tranches laid down in Article 49.1 of these special conditions are determined so that the pre-financing is fully repaid before provisional acceptance.

Article 18	Retention monies

18.1	The sum retained to guarantee implementation of the contractor’s obligations during the defects liability period is 5 % of the contract price. By derogation to Article 47.1 of the general conditions, that money is not retained from interim payments. The tranches laid down in Article 49.1 of these special conditions are determined so that the retention sum amounts to 5% of the contract price at the moment of the certificate of provisional acceptance.

18.2	By derogation to Article 47.2 of the general conditions, the retention sums cannot be substituted by a retention guarantee.

Article 19	Price revision

19.1	Prices are fixed and shall not be revised.

Article 20	Measurement

20.1	This is a lump-sum contract.

Under the conditions imposed by the special conditions and general conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 20% | Lump-sum advance Article 17 | After conclusion of the contract against the pre-finance guarantee |
| 2. | 75% | Interim payments | Interim payments are to be done every month based on scope of works that are completed by the contractor and accepted by the site supervisor The frequency of the interim payment shall be made maximum once per each calendar month |
| Last | 5% | Retention money Article 18 | Within 60 days of the issuing of the signed final statement of account (retention guarantee) |

Article 21	Interim payments

21.1	The interim payments will be paid as determined in Article 20.1 of these special conditions.

Article 22	Defects liability

22.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the supervisor or the contracting authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the general conditions.

Article 23	Dispute settlement

23.1	Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of Georgian Courts in accordance with the national legislation of the state of the contracting authority

Article 24	Data protection

1. Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of the state of the contracting authority and with the provisions of the respective financing agreement.

2. To the extent that the contract covers an action financed by the European Union, the Contracting Authority may share communications related to the implementation of the contract, with the European Commission. These exchanges shall be made to the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the financing agreement with the Partner country – contracting authority. The exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, staff, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsel). In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Commission. When personal data is transmitted to the Commission, the latter processes them in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC and as detailed in the specific privacy statement published at ePRAG.

OJ L 205 of 21.11.2018, p. 39