Reference No.: GRETA-SC-176/2023

Terms of Reference

**Market linkage analysis and regional B2B meeting/forum organizing service**

Project/Programme Title: **GRETA | Green Economy: Sustainable Mountain Tourism and Organic Agriculture**

Country: **Georgia**

ADA Contract Number: **ADA ID No. 6542-00/2018**

EU Identification Number: **EU ID No. ENI/2018/401-348**

Implementer: **Austrian Development Agency (ADA)**

Budget Line: **6.7.3**

Name of Partner/Donors Organizations: **European Union Delegation, Swedish Embassy, Austrian Development Cooperation**

# Introduction and background:

Agriculture and tourism constitute two essential sectors of income in the rural high mountain areas of Georgia.

In 2021, despite the pandemic, the **Georgian agri-food sector** showed significant positive results. According to preliminary data, the total production indicator of agribusiness products (production of primary agricultural products and products obtained through processing) amounted to about 4.2 billion euros (32.5% higher than the 2018 figure); the added value indicator was 1.2 billion euros (22.1% higher than the 2018 figure); the average monthly income of rural households calculated per one household was 320 euros (11.6% higher than in 2018).

In the same period, the persistence of the pandemic has continued affecting the **tourism sector** dramatically: the foreign exchange income from international travel (480 million EURO) was 83.4% lower than in 2019; the total value added in the tourism sector fell by 29.8%; the gross value from tourism industries as a proportion of GDP decreased from 8.4% to 5.9%. The mountainous protected areas showed a decline of number of visitors of 80% compared to the previous year and the income from tourism services registered a fall of 90.4% since 2019.

The **overall objective** of GRETA | Green Economy: Sustainable Mountain Tourism and Organic Agriculture is to facilitate an improvement of the business environment and the creation of new income opportunities in sustainable mountain tourism and organic agriculture to reduce poverty and exclusion in the selected mountain areas of Georgia.

The **expected outcomes** are:

1. The legal and policy framework for sustainable mountain tourism and organic agriculture is enabling sustainable and inclusive development;
2. Employment and income in both sectors are increased due to new and better products and services and through better market linkages, locally, nationally and internationally;
3. Access to capacity development measures for people and institutions active in the fields of sustainable mountain tourism and organic agriculture is improved and a system of knowledge management is in place enabling joint learning among public, private and civil society actors.

The **project targeted** area consists of eight municipalities in the regions of Upper Imereti (municipalities of Sachkhere, Tkibuli, Chiatura), in Racha-Lechkhumi-Lower Svaneti (municipalities of Ambrolauri, Oni, Tsageri, Lentekhi) and in Upper Svaneti (municipality of Mestia).

**Direct beneficiaries** of GRETA are going to be at least 400 small-scale business enterprises and producers in mountain tourism, 300 accommodation service providers, 300 other tourism service suppliers like tour operators (climbing-, hiking-, bicycle-, walking-, horseback-, historical- and culinary tours), tourism information centres associations and DMOs (Destination Management Organizations), 230 farmers involved in organic agriculture certification, 2 certification bodies, 76 local villagers and inspectors specialized in selected local value chains.

**Indirect beneficiaries** on the central level are six Ministries and public institutions (Ministry of Economy and Sustainable Development, Ministry of Environmental Protection and Agriculture, Ministry of Regional Development and Infrastructure, Enterprise Georgia, Georgian National Tourism Administration), some 70 extension service staff and other MEPA-representatives at municipality and central level, 6 associations, retailers and online food stores, agricultural colleges and training institutions, several thousand tourists, and thousands of consumers of organic products.

GRETA project is implemented between **2019 and 2023**.

The **project budget** totals € 6.8 Million Euros and consists of contributions of the EU (€ 3 mill.), Sweden (€ 2.8 mill.) and the Austrian Development Cooperation (€1.0 mill.).

The **governance** of the GRETA project is guaranteed by a Programme Steering Committee (SC) and an Advisory Committee (AC), where the three donors plus representatives of various government agencies are represented.

Further information about the GRETA project: [www.gretaproject.ge](http://www.gretaproject.ge)

# Objective(s) of the Assignment:

The purpose of the assignment is for a highly professional marketing and event company to analyze and conduct regional B2B meeting/forum enabling the activity as a sample model to scale up the domestic market linkages for SMEs operating in the organic agriculture and tourism field.

1. Analyse potential market linkages within the GRETA beneficiaries
2. Identify business matching
3. Organize regional B2B meeting/forum

# Tasks to be conducted:

The selected company shall be contracted/funded to perform the following tasks:

1. Business scope analysis
2. Review business scope description as well as the Monitoring and Evaluation reports for 25 SMEs in tourism field and 39 Beneficiaries in Organic Agriculture field.
   1. Conduct online brief interviews with beneficiaries if necessary.
   2. Analyze business needs and capacities for all the mentioned beneficiaries.
3. Business match
   1. Elaborate business matching matrix
   2. Based on the matching matrix to Identify the most prosperous businesses for potential domestic market linkages according to the set criteria such as sustainability, gender equality, capacity, effectiveness, or any other internationally recognized criteria.
4. B2B meeting/forum
   1. Conduct B2B meeting/forum for identified/selected SMEs based on the following concept:

|  |  |  |
| --- | --- | --- |
| **#** | **Topic** | **Description** |
| 1 | Location: Kutaisi | The most optimal location connecting 3 targeted regions of the GRETA project. |
| 2 | Duration | Up to 3 days |
| 3 | Moderator | 1 general moderator / 10 sectoral specific moderator/facilitator |
| 4 | Space | Conference room accommodating up to 50 persons and space for accommodating up to 10 B2B group meetings ( B2B meetings are not necessary at the same time, but throughout the event activity days). |
| 5 | Logistics (full route) and accommodation | Ensuring transportation of beneficiaries:  Considering maximum number of beneficiaries (25 SMEs in tourism field and 39 SMEs in agriculture field) the locations are distributed as follows:  Tourism component:   * 10 from Ambrolauri municipality * 2 from Chiatura municipality * 6 from Mestia municipality * 4 from Oni municipality * 2 from Tkibuli municipality * 1 from tsageri municipality   Agriculture component:   * 7 from Ambrolauri Municipality * 3 from Oni municipality * 10 from Chiatura municipality * 4 from lentekhi municipality * 5 from Mestia Municipality * 2 from Tkibuli municipality * 8 from tsageri municipality   Ensuring accommodation, internal transportation and full board for the mentioned beneficiaries. |
| 6 | LED screen | 3 X 4 m dimensions |
| 7 | Facilities | Microphone and stage/conference facilities |
| 8 | Visibility | 10 roll up banners. (Standard 80X2)  10 table flags (EU/Sweden/Austria/GEO) |

NOTE #1: Target of the activity is to encourage up to 25 SMEs operating in tourism sector and having capacity to establish sustainable domestic linkages

NOTE #2: Gender equality approach is crucial, whereas up to 33% involved SMEs should be run by women

In undertaking these activities, the consultants will adopt a fully consultative and participative approach, particularly when working with agreed beneficiaries. The firm will work closely with GRETA project staff and GRETA project Marketing Expert Company as appropriate.

To achieve the outputs and results, the assignment should involve using a full range of methodologies. The consultant applicants should be able and prepared to use all the methodologies open to them to achieve the objectives of the assignment.

Consultants should be prepared to travel independently with support from GRETA field offices in arranging meetings and consultations.

# Deliverables:

|  |  |  |
| --- | --- | --- |
| **#** | **Deliverables** | |
| 1 | **Workplan** | A brief high-quality document describing work approach and detailed implementation plan |
| 2 | **Business scope analysis** | A comprehensive and high-quality document - a detailed analysis and assessment of SME’s supplemented by the relevant proofs and annexes. (25 SMEs from tourism component and 39 SMEs from organic agriculture component) |
| 3 | **Business match** | High-quality documents, clearly explain the business matching matrix for mentioned SMEs and highlighting the most prosperous business and market linkages, considering the gender equality approach. |
| 4 | **B2B meeting/forum concept note** | High-quality documents for describing B2B meeting/forum engaging the most prosperous businesses for potential domestic market linkages according to the set criteria such as sustainability, gender equality, capacity, and effectiveness or any other internationally recognized criteria. |
| 5 | **Conducing one B2B meeting/Forum** | B2B meeting/forum report for identified/selected SMEs and based on the agreed concept |
| 6 | **Mid-term progress report** | Brief document(s) describing the working progress including project coordination and all the relevant administrative recordings. |
| 7 | **Final report combining all the deliverables** | A compilation of all documents, reports, deliverables, assumptions, and concerns. |

# Timeline and Milestones

The project must be completed by 15th September 2023.

# Size and Qualifications of the Assessment Team

Collectively, the team will be expected to include a balance experts, context, content, and process to successfully complete this assignment.

**Minimum Required Personnel**

|  |  |
| --- | --- |
| REQUIRED PERSONNEL | Minimum Years of Experience in Handling either National or international wide Accounts |
| 1. Project team leader | 10 years |
| 1. Project coordinator | 5 years |
| 1. Business analyst | 5 years |
| 1. Marketing Expert | 5 years |
| 1. Event manager | 5 years |
| 1. Administrative assistant | 3 years |

*Note: Bidders is free to recommend additional personnel that is deemed to be fit for the Team*

# Qualification and Eligibility

* The firm/ to be selected must be an organization or institution that has at least 5 years’ experience or the team should have at least 5 years’ experience in branding, marketing and events.
* Given the complexity of tasks and the ambitious results, it is expected that the Contractor should engage qualified expert as team leader to ensure the high quality of the project.
* The firm must be capable of advising the client on how to achieve the set goals in efficient manner.
* The firm may have a tie-up or joint venture arrangement with other local or international agencies to execute the project. It may also have a joint venture with a global company.

# Evaluation and Selection:

The overall proposal will consist of two separate parts - the **technical proposal** and **financial proposal**. Proposals should be prepared as per format below and they will be evaluated based on the scoring criteria mentioned here below. Bidders are also encouraged to avoid overly generic proposal language and instead provide a contextually appropriate, descriptive, and specific plan for managing the activities and reaching the expected deliverables.

**Technical Bid/Proposal Criteria and Rating**

|  |  |  |
| --- | --- | --- |
| CRITERIA | DESCRIPTION | RATING |
| Capability of the bidder | Minimum Required Personnel | **30%** |
| Team composition / Pool of Experts |
| Methodology (proposed framework) |
| Quality of Personnel to be assigned to the project | Market Research and analysis | **30%** |
| Eexpertise in project management |
| Eexpertise in marketing |
| Eexpertise in event |
| Eexpertise in consulting |
| Project management Plan | Team structure/roles and responsibilities | **10%** |
| Timeframe |
| Financial Offer | The financial proposal should indicate professional fees, including the level of people and number of days and out-of-pocket costs like travel, per diems, etc. | **30 %** |
| TOTAL | | **100%** |

Note technical proposal should not exceed 20 Pages.

# List of the required documents

* The **TECHNICAL PROPOSAL** should include:
  + Company profile
  + Institutional Capacity and Past Performance;
  + Proposed Methodology/Framework;
  + Detailed project implementation timeframe (per task);
  + CV(s) of the Personnel(s);
  + At least two signed references that are independent from each other;
* The **Financial Proposal** in EURO Gross excluding VAT:
  + Budget template is attached;
  + Organization Identification Number.

\*You can check the VAT exemption status effective within Georgia at RS.GE (ID: 205305560)

**Financial proposal not compliant with the budget template will be rejected.**

**Applicants submitting proposal via Cloud Base sources (e.g Wetransfer) will not be considered eligible for evaluation process.**

# Deadlines and Submission:

**Questions for clarification** can be addressed to [**mariam.tsereteli@ada.gv.at**](mailto:mariam.tsereteli@ada.gv.at) before **07.06.2023 17:00**. The response to submitted questions will be supplied no later than **08.06.2023 17:00**.

Non-binding offer free of charge in the English language should be submitted via Email to [**mariam.tsereteli@ada.gv.at**](mailto:mariam.tsereteli@ada.gv.at) before **13.06.2023 17:00**. in the form of two separate, signed, documents in pdf format. One document clearly marked TECHNICAL PROPOSAL and one document clearly marked FINANCIAL proposal. Please indicate “**CFP – Market linkage analysis and regional B2B meeting/forum organizing service**” in the subject line.

The GRETA project/ADA, its donors and implementing company reserve the right to reject all proposals and cancel, reschedule and/or stop the call for Expression of Interest and/or Tender at any time.

# Processing of Personal Data

During initiation and performance of contracts, ADA may process personal data of natural persons that are collected by ADA or transferred or disclosed to ADA by prospective contractors or third parties under their instruction, e.g., personal data of employees, legal representatives, agents or other partners of the prospective contractors or such third parties.

By submitting information to ADA, you, as a prospective contractor, acknowledge:

* to have taken note of ADA’s Privacy Notice <https://www.entwicklung.at/en/media-centre/privacy-notice> (’ADA Privacy Notice’);
* to ensure that each direct or indirect transfer or disclosure of personal data to ADA during the initiation or performance of a contract is lawful pursuant to applicable data protection law;
* to ensure that all persons, whose personal data are transferred or disclosed to ADA, were promptly and demonstrably provided the ADA Privacy Notice; and
* that if a contract is concluded and in accordance with its terms, ADA publishes, in particular on the ADA website, information about the contract and the contracting parties.

# Other conditions:

The technical teams of the contracted firm will be required to use their own laptops and submit all deliverables in digital format. The offeror is expected to plan for the team’s workspace, conference facilities, telecommunications, printing, and any other needs necessary for completing the activities.

## Confidentiality:

The materials produced during the period of this consultancy will be treated as strictly confidential, and the rights of distribution and/or publication will reside with GRETA/ADA. Use or re-publication of any material by the contractor will not in any way be permitted.

## Nature of Penalty Clause to be stipulated in the contract:

GRETA/ADA reserves the right not to pay the Contractor or withhold part of the payable amount if one or more requirements established for this assignment are not met or the deadline set for the accomplishment of the tasks is missed.

## Contract:

The selected company will be awarded a maximum 9 months -long contract starting from the day of signature.

## Payment Schedule:

Payments will be based on deliverables and will be made in local currency (GEL) converted from EURO in the date of payment and within 10 days upon delivery, based on GRETA’s satisfactory review of services specified in terms of Reference and the formal approval. Nature of Penalty Clause to be stipulated in the contract:

GRETA/ADA reserves the right not to withhold all or a portion of payment if performance is unsatisfactory, if work/outputs are incomplete, or if not delivered for failure to meet deadlines.

## Working language:

GRETA/ADA project working languages are Georgian and English, and communication, meetings, documentation, deliverables, etc., have to be bilingual.

## Support provided by GRETA:

GRETA will regularly communicate with the contractors and provide feedback and guidance and necessary support to achieve the objectives of the work, as well as remain aware of any upcoming issues related to the performance and quality of work. GRETA will provide the contractors with:

* Basic information on the projects (reports, earlier developed human stories, GRETA -branded pictures);
* Branding and other GRETA guidelines on multi-media materials.
* Suggestions on the most suitable project sites, stories, and relevant contacts.

## Copyrights & utilization rights:

The copyright of all materials produced (raw and edited) taken during the assignment will belong to GRETA/ADA.

## Code of conduct:

Code of conduct during the term of consultancy: the GRETA/ADA Code of Conduct must be signed and thoroughly followed by the consultant.